## MINOR WORKS
REVISED SIMPLIFIED PROCUREMENT PLAN FOR ACE PROJECT 2014/2015
1. | General THE EXCHANGED RATE USED IS ₦200 PER US DOLLAR
| Country/Organisation: | BENUE STATE UNIVERSITY,NIGERIA
| Project/Programme: | Center of Excellence in the control of post harvest losses(center for food technology and research)
Loan No:
| Implementing Agency, Address: | BENUE STATE UNIVERSITY,MAKURDI,NIGERIA
World Bank's Approval Date of Procurement Plan:
Date of General Procurement Notice:
| Period Covered by these Procurement Plans: | January, 2016 – December, 2016
MINOR WORKS
2. | Prior Review Threshold:
| Procurement Method | Threshold for use of Method (US$) | Prior review Threshold (US$) | Comments
| 1. ICB and LIB (Goods) | N/A | N/A
| 2. NCB (Goods) | N/A | N/A
| 1. ICB (Works) | N/A | N/A
| 4. NCB (Works) | N/A | N/A
| 5. ICB (Non-Consultant Services) | N/A | N/A
| 6. Shopping | N/A | N/A
| 7. Direct Contracting | N/A | N/A
3. | Procurement Packages with Methods and Time Schedule |  | BASIC DATA | [7 empty] | Bid Documents |  | Bidding Period |  | Bid Evaluation |  | Contract Award |  |  | Contract Implementation |  | DISBURSEMENT LINKED INDICATORS
| Description of Contract | Source of Funds | Estimated Amount (US$) | Procurement Method | Pre-or Post Qualification | Dom/Reg. Preference (Y/N) | Prior or Post Review | Expected Date Issue of Bid Docs | Expected Bid closing Date | Plan vs. Actual | Transmission Bid Docs Date | No-objection Date | Bid Invitation Date | Bid Closing-Opening | Bid Evaluation Report | No-objection Date | Contract Amount (US$) | Contract Award Date | Contract Signature Date | Start Date | End Date | DLI/DLR
| Rehabilitating Existing Facilities : ( Laboratories and refurblishing of additional | WB | 55150 | NCB | Post- Qualification | N/A | Post Review | 9th-june-16 | 7th-july-16 | Plan | N/A | N/A | 9th-june-16 | 7th-july-16 | 2016-08-17 | N/A | 55,150.00 | 29th-sept-16 | 30th-sept-16 | 29th-sept-16 | 19th-dec-16
Actual
| construction of PG faculty for CEFTER | WB | 300250 | NCB | Post- Qualification | N/A | Post Review | 9th-june-16 | 7th-july-16 | Plan | N/A | N/A | 9th-june-16 | 7th-july-16 | 2016-08-17 | N/A | 300,250.00 | 29th-sept-16 | 30th-sept-16 | 29th-sept-16 | 24th-march-17
Actual
| Establishing of language support unit | WB | 19900 | NCB | Post- Qualification | N/A | Post Review | 9th-june-16 | 7th-july-16 | Plan | N/A | N/A | 9th-june-16 | 7th-july-16 | 2016-08-17 | N/A | 19,900.00 | 29th-sept-16 | 30th-sept-16 | 29th-sept-16 | 24th-march-17
Actual
| Total Cost |  | 375300

## GOODS
REVISED SIMPLIFIED PROCUREMENT PLAN FOR ACE PROJECT 2014/2015
1. | General THE EXCHANGED RATE USED IS ₦200 PER US DOLLAR
| Country/Organisation: | BENUE STATE UNIVERSITY,MAKURDI,NIGERIA
| Project/Programme: | Center of Excellence in the control of post harvest losses(center for food technology and research)
Loan No:
| Implementing Agency, Address: | BENUE STATE UNIVERSITY,MAKURDI,NIGERIA
World Bank's Approval Date of Procurement Plan:
Date of General Procurement Notice:
| Period Covered by these Procurement Plans: | January, 2016– December, 2016
G O O D S
2. | Prior Review Threshold:
Goods and Non-Consulting (see Note 1)
|  | Threshold | Prior review
| Procurement Method | for use of Method | Threshold | Comments
|  | (US$) | (US$)
| 1. ICB and LIB (Goods) | N/A | N/A
| 2. NCB (Goods) | N/A | N/A
| 1. ICB (Works) | N/A | N/A
| 4. NCB (Works) | N/A | N/A
| 5. ICB (Non-Consultant Services) | N/A | N/A
| 6. Shopping | N/A | N/A
| 7. Direct Contracting | N/A | N/A
3. | Procurement Packages with Methods and Time Schedule |  | BASIC DATA | [7 empty] | Bid Documents |  | Bidding Period |  | Bid Evaluation |  | Contract Award |  |  | Contract Implementation |  |  | DISBURSEMENT LINKED INDICATORS
| Description of Contract | Source of Funds | Estimated Amount (US$) | Procurement Method | Pre-or Post Qualification | Dom/Reg. Preference (Y/N) | Prior or Post Review | Expected Date Issue of Bid Docs | Expected Bid closing Date | Plan vs. Actual | Transmission Bid Docs Date | No-objection Date | Bid Invitation Date | Bid Closing-Opening | Bid Evaluation Report | No-objection Date | Contract Amount (US$) | Contract Award Date | Contract Signature Date | Start Date | End Date | DLI/DLR | REMARKS
LOT 1 RESEARCH/LABORATORY EQUIPMENT
| Purchase of Research Equipment | WB | 150571.43 | NCB | Post- Qualification | N/A | Post Review | 2nd-june-16 | 29th-june-16 | Plan | N/A | N/A | 2nd-june-16 | 29th-june-16 | 20th-july-16 | N/A |  | 23rd-aug-16 | 30th-aug-16 | 30th-aug-16 | 3rd-oct-16
Actual
LOT 2 LABORATORY EQUIPMENT
| Provision of advanced laboratory equipment | WB | 200287.71 | NCB | Post- Qualification | N/A | Post Review | 2nd-june-16 | 29th-june-16 | Plan | N/A | N/A | 2nd-june-16 | 29th-june-16 | 20th-july-16 | N/A |  | 23rd-aug-16 | 30th-aug-16 | 30th-aug-16 | 3rd-oct-16
Actual
LOT 3 STATIONARY/ STAFF COMPUTERS
| Purchase of stationary and staff computers | WB | 40000 | Shopping | Post- Qualification | N/A | Post Review | 2nd-june-16 | 29th-june-16 | Plan | N/A | N/A | 2nd-june-16 | 29th-june-16 | 20th-july-16 | N/A |  | 23rd-aug-16 | 30th-aug-16 | 30th-aug-16 | 3rd-oct-16
Actual
LOT 4 FURNISHING OF CLASSROOMS
| Use of ICT in delivering Research Excellence :provision of CEFTER PG interactive classroom | WB | 26507.14 | Shopping | Post- Qualification | N/A | Post Review | 2nd-june-16 | 29th-june-16 | Plan | N/A | N/A | 2nd-june-16 | 29th-june-16 | 20th-july-16 | N/A |  | 23rd-aug-16 | 30th-aug-16 | 30th-aug-16 | 3rd-oct-16
Actual
| TOTAL |  | 417366.28
NOTE:
1. In LOT3 and LOT, we apply the shopping procurement procurement method since these items are off-shelf items andwould be carried out more than once as needed.

## CONSULTANCY SERVICES
REVISED SIMPLIFIED PROCUREMENT PLAN FOR ACE PROJECT 2014/2015
1. | General THE EXCHANGED RATE USED IS ₦200 PER US DOLLAR
| Country/Organisation: | BENUE STATE UNIVERSITY NIGERIA
| Project/Programme: | Center of Excellence in the control of post harvest losses(center for food technology and research)
Loan No:
| Implementing Agency, Address: | BENUE STATE UNIVERSITY,MAKURDI,NIGERIA
World Bank's Approval Date of Procurement Plan:
Date of General Procurement Notice:
| Period Covered by these Procurement Plans: | January, 2016 – December, 2016
CONSULTANCY SERVICES
2. | Prior Review Threshold:
Consultants (see Note 3)
|  |  | Threshold | Prior review
| Procurement Method |  | for use of Method | Threshold | Nature of Goods
|  |  | (US$) | (US$)
| 1. Quality and Cost Based Selection (QCBS) |  | N/A | N/A
| 2. Consultants Qualification Selection (CQS) |  | N/A | N/A
| 3. Least Cost Selection (LCS) |  | N/A | N/A
| 4. Fixed Budget Selection (FBS) |  | N/A | N/A
| 5. Selection of Individual Consultants (SIC) |  | N/A | N/A
| 6. Single Source Selection (SSS) |  | N/A | N/A
3. | Procurement Packages with Methods and Time Schedule | [8 empty] | Request for Expression of Interest |  |  |  |  | Request for Proposal & Short List |  | Proposals |  | Bid Evaluation Technical (T) & Financial (F) |  |  |  |  | Contract Award |  |  | Contract Implementation |  | DISBURSEMENT LINKED INDICATORS
| Description of Assignment | Source of Funds | Estimated Amount (US$) | Selection Method | Prior/Post Review | Lumpsum or Timed-Based | Plan vs. Actual | Submission Date | No-objection Date | Date Published | Submission Date | Plan vs. Actual | Submission Date | No-objection Date | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | No-objection Evaluation Report (T) | Opening Financial Proposals | Submission Eval Report (T) & (F) | Submission Negotiations Report | No-objection Award & Negotiations | Plan vs. Actual | Contract Amount (US$) | Contract Award Date | Contract Signature Date | Start Date | End Date | DLI/DLR
| Support Services to CEFTER | WB | 150000 | LCS | Post Review | Lumpsum | Plan | NA | NA | NA | NA | N/A | N/A | N/A | N/A | N/A | 24th-june-16 | 22nd-july-16 | N/A | N/A | N/A | N/A | N/A |  | 1-20 Weeks | 1-20 Weeks | 1-20 Weeks | 1-26 Weeks
Actual
| upgrading established effective quality assurance and quality improvement policy | WB | 20000 | LCS | Post Review | Lumpsum | Plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | 10th-june-16 | 4th-july-16 | N/A | N/A | N/A | N/A | N/A
Actual
| Produce a financial Manual for CEFTER (consistent with the State, National and international financial best practices) | WB | 7000 | LCS | Post Review | Lumpsum | Plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | 14th-june-16 | 30th-june-16 | N/A | N/A | N/A | N/A | N/A
Actual
| Provide a strong data management policy for CEFTER (Cosultancy charge) and implementation | WB | 4500 | SSS | Post Review | Lumpsum | Plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | 24th-june-16 | 22nd-july-16 | N/A | N/A | N/A | N/A | N/A
Actual
| consultancy services for the construction of PG faculty for cefter complex | WB | 45037.5 | LCS | Post Review | Lumpsum | Plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | 17th-Augst-16 | 16th-sept-16 | NA | NA | NA | NA | NA
Actual
| Provide an ICT policy for CEFTER (Cosultancy charge) and implementation | WB | 6000 | SSS | Post Review | Lumpsum | Plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | 5th-sept-16 | 22nd-sept-16 | N/A | N/A | N/A | N/A | N/A
Actual
| Total Cost |  | 232500
Note
Please refer to the Bank's comments for enable make the required amendments.
|  | Please note that the yellow cells do not require dates, as the project would not be required to send to the WB for Clearance. | [6 empty] | Project should replace the dates with Not Applicable " NA".
1
2

## OPERATING COST
REVISED SIMPLIFIED PROCUREMENT PLAN FOR ACE PROJECT 2014/2015
1. | General THE EXCHANGED RATE USED IS ₦200 PER US DOLLAR
| Country/Organisation: | BENUE STATE UNIVERSITY NIGERIA
| Project/Programme: | Center of Excellence in the control of post harvest losses(center for food technology and research)
Loan No:
| Implementing Agency, Address: | BENUE STATE UNIVERSITY,MAKURDI,NIGERIA
World Bank's Approval Date of Procurement Plan:
Date of General Procurement Notice:
| Period Covered by these Procurement Plans: | January, 2016–December, 2016
OPERATING COST
2. | Prior Review Threshold:
|  | Threshold | Prior review
| Procurement Method | for use of Method | Threshold | Comments
|  | (US$) | (US$)
| 1. ICB and LIB (Goods) | N/A | N/A | N/A
| 2. NCB (Goods) | N/A | N/A | N/A
| 1. ICB (Works) | N/A | N/A | N/A
| 4. NCB (Works) | N/A | N/A | N/A
| 5. ICB (Non-Consultant Services) | N/A | N/A | N/A
| 6. Shopping | N/A | N/A | N/A
| 7. Direct Contracting | N/A | N/A | N/A
3. | Procurement Packages with Methods and Time Schedule |  | BASIC DATA | [6 empty] | DISBURSEMENT LINKED INDICATORS
| Description of Expenses | Source of Funds | Estimated Amount (US$) | 1st quarter | 2nd quarter | 3rd quarter | 4th quarter | Total Amount (US$) | Plan Vs Actual | DLI/DLR
| Audit expenses (Procurement and Account audit) | WB | 17500 |  | 4000 | 6000 | 7500 | 17500 | Plan
Actual
| Employment and training technicians and qualified support staff (Training of staff on new equiptment and recruitment process fees) | WB | 30000 |  | 7500 | 10500 | 12000 | 30000 | Plan
Actual
| Student recruitment (Advertisements, portal, travels, interview and printing) | WB | 13500 |  |  | 7000 | 6500 | 13500 | Plan
Actual
| Scaling up PhD Programmes (increasing students numbers,visiting and professors and researchers) Honoraria of non employed staff) | WB | 36000 |  | 9000 | 13500 | 13500 | 36000 | Plan
Actual
| International Research Collabration and Joint Research Programme among students faculties | WB | 60000 |  | 15000 | 22500 | 22500 | 60000 | Plan
Actual
| Local Travels | WB | 24000 |  | 6000 | 9000 | 9000 | 24000 | Plan
Actual
| Faculty Developments :capacity building in curricala and non based programmes | WB | 50000 |  | 12500 | 19000 | 18500 | 50000 | Plan
Actual
| Research grant pools (to small and medium scale applied research) | WB | 23000 |  | 5000 | 8500 | 9500 | 23000 | Plan
Actual
| Publication in high impact factor journals by faculty and students (cost of publication) | WB | 15000 |  | 3500 | 5500 | 6000 | 15000 | Plan
Actual
| Provide equitable distribution of excellence through affiliation to other institutions (Travels and mettings) | WB | 10500 |  | 2500 | 4000 | 4000 | 10500 | Plan
Actual
| Provide equitable distribution of excellent high quality open and distant learning | WB | 35000 |  | 8750 | 13500 | 12750 | 35000 | Plan
Actual
| Provide equitable distrbution of excellence and high quality research by instituting doctoral research | WB | 20000 |  | 5000 | 7500 | 7500 | 20000 | Plan
Actual
| provide broad-based scientific capacity of students through intenships, short courses and SIWES | WB | 40000 |  | 10000 | 15000 | 15000 | 40000 | Plan
Actual
| Provision of extension and community mobilization services/awareness | WB | 15000 |  | 3500 | 5500 | 6000 | 15000 | Plan
Actual
| Ensure social relevance through annual regional stakeholders meeting in participating countries NRCRI | WB | 15000 |  | 3500 | 6000 | 5500 | 15000 | Plan
Actual
| Engagement in joint research project among participating institutions | WB | 16000 |  | 4000 | 6000 | 6000 | 16000 | Plan
Actual
| Introdution of regional working groups for research groups | WB | 16000 |  | 6000 | 4000 | 6000 | 16000 | Plan
Actual
| Short term exchange programmes within Nigeria | WB | 15000 |  | 4000 | 5500 | 5500 | 15000 | Plan
Actual
| Schorlaships research for Cefter Students and | WB | 150000 |  | 35000 | 55000 | 60000 | 150000 | Plan
Actual
| Introdution of short term (professional) courses (design special Agro Bussiness start-up courses for loan takers) | WB | 15000 |  | 5000 | 5500 | 4500 | 15000 | Plan
Actual
| Research grant pools to support faculty and student's international applied research on post-harvest losses | WB | 16000 |  | 4000 | 6000 | 6000 | 16000 | Plan
Actual
| Workshop at AOCAY partner. | WB | 15000 |  | 4000 | 5500 | 5500 | 15000 | Plan
Actual
| Development joint curricula among partnership institution and CEFTER departments | WB | 15000 |  | 5000 | 5500 | 4500 | 15000 | Plan
Actual
| Identification of joint training needs for academic and professional staff in post-harvest science and management | WB | 12000 |  | 3000 | 4500 | 4500 | 12000 | Plan
Actual
| Stakeholders meeting to review progress at ACE | WB | 12000 |  | 3000 | 5000 | 4000 | 12000 | Plan
Actual
| Domestication of curricula in the departments at BSU (Independent review of draft curricula) | WB | 6000 |  | 1500 | 2000 | 2500 | 6000 | Plan
Actual
| Faculty and students training (Staff on PG fellowship) | WB | 20000 |  | 5000 | 7500 | 7500 | 20000 | Plan
Actual
| Mount short courses,workshops and conferences on topics in post-harvest sciences and management (Food Safety and Hygiene) | WB | 15000 |  | 4000 | 4500 | 6500 | 15000 | Plan
Actual
| Institute lecture series: NSPRI organised on Impact of Climate change on PHL | WB | 10000 |  | 2500 | 3000 | 4500 | 10000 | Plan
Actual
| Produce and circulate monographs targeted at awareness creation and extension to rural farmers | WB | 6000 |  | 2000 | 2500 | 1500 | 6000 | Plan
Actual
| Support Research fellowships( Sponsor staff of partner institutions on PG programs) | WB | 15000 |  | 3500 | 6000 | 5500 | 15000 | Plan
Actual
| Plan for achieving collaborations with International partners Joint research and Accredition activities (partnership Funding/activities with LJMU) | WB | 35000 |  | 6000 | 15000 | 14000 | 35000 | Plan
Actual
| Start long faculty exchanges between CEFTER, and Universities in Africa | WB | 24000 |  | 6000 | 10000 | 8000 | 24000 | Plan
Actual
| Start of joint research projects between CEFTER,universties and research insttutes elsewhere in Africa | WB | 15000 |  | 3500 | 6000 | 5500 | 15000 | Plan
Actual
| Appoint Governing Board of CEFTER (Travel and refreshments) | WB | 7000 |  | 3500 | 3500 |  | 7000 | Plan
Actual
| Produce operational manuals for students | WB | 6000 |  |  | 3000 | 3000 | 6000 | Plan
Actual
| Monitoring and evaluation (Travels, stationaries) | WB | 18000 |  | 4500 | 7000 | 6500 | 18000 | Plan
Actual
| Fund raising activities (Meetings, travels, media) | WB | 10500 |  | 2500 | 4500 | 4500 | 10500 | Plan
Actual
| NgREN Communication Services | WB | 300000 |  | 50000 | 130000 | 120000 | 300000 | Plan
Actual
| Casual staff on Utility services (Cleaners, security) | WB | 40000 |  | 10000 | 14000 | 16000 | 40000 | Plan
Actual
| Provide Automated accounting System | WB | 20000 |  | 6000 | 6500 | 7000 | 20000 | Plan
Actual
|  | TOTAL | 1234500 | 0 | 279250 | 480500 | 474750 | 1234500
NOTE:
1. operating manuals for students are produced every year.

## SUMMARY
SUMMARY
THE EXCHANGED RATE USED IS ₦200 PER US DOLLAR
GOODS
| LOT 1 : RESEARCH/LABORATORY EQUIPMENT | I50,571,43
| LOT 2 : LABORATORY EQUIPMENT | 200287.71
| LOT 3 : STATIONARY/ STAFF COMPUTERS | 40000
| LOT 4 :FURNISHING OF CLASSROOMS | 26507.14
TOTAL |  |  | 417366.28
MINOR WORKS |  |  | 375300
| CONSULTANCY SERVICES |  | 232500
OPERATING COST |  |  | 12345000
GRAND TOTAL |  |  | 2259666.28