## Sheet1
Name of Center: Center for Food Technology and Research (CEFTER)
Institution: Benue State University |  |  |  | On Schedule
Country: Nigeria
Center Leader: Dr. Barnabas Achakpa Ikyo |  |  |  | Behind Schedule
Annual Workplan (January-April, 2025)
Work Plan Activities | Description | Partner Contribution (if relevant) | 2025 Y2Q1 |  |  | 2025 Y2Q2 |  |  | 2025 Y2Q3 |  |  | 2025 Y2Q4 |  |  | Milestone/Output | If NEW, Provide Justification | Estimated Budget($) | Estimated Revenue ($) | Contribution from Partner ($) | Person Responsible
|  |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Action 1: DLI 2 Institutional Impact
Sub-Action 2a: Regional/National Conference and Seminar by Staff and Students
Activity 1: Collaboration with FOOD4WA on ongoing Regional seminar series | Coordination of participation by staff and Students | [13 empty] | Mainstreaming of improved learning and teaching methods in the institutions |  | 2000 |  |  | Centre Management
Activity 2: Sponsorship of staff and students on regional/national/international conference | Sponsor a minimum of 3 staff on conferences | [15 empty] | 10000
Sub-Action 2b: Post-harvest Clinic/activities
Activity 1: Conduct needs assesment to identify Communities for participatory conduct of a virtual Post-Harvest Clinic workshop | Identify Communities for participatory conduct of a virtual Post-Harvest Clinic | Suggest new techniques | [12 empty] | Community members adopt improved techniques for food preservation and processing |  |  |  |  | Centre Management
Activity 2: Draft report for consideration by Technical Committee | Present considerations to technical committee for
Activity 3: Design curriculum and contact resource persons | Conduct clinic and training | Participate in trainings | [14 empty] | 10000
Action 2: DLI 3: Quantity of Students
Sub-Action 3a: Implementation of modules developed from the training on
Activity 1: Identify suitable individuals/communities to test run the modules | Hold a meeting to set out modalities for the training | Participate in meetings | [12 empty] | Use of new modules by farmers/food handlers to improve their income |  |  |  |  | Centre Management
Activity 2: Train community members in the use of developed modules | Identify modules that are suitable for the training | Suggest modules | [14 empty] | 10000
Sub-Action 3b: Training of Technologist and Laboratory staff on more specialised equipment
Activity 1: Identify the new specialised equipment and conduct training | Identify the new specialised equipment and conduct training | [13 empty] | Trained laboratory technologists deployed to the departments |  | 2000 |  |  | Centre Management
Activity 2: Payment for softwares, licence subscriptions | Payment for softwares, licence subscriptions | [15 empty] | 10000
Sub-Action 3c: Training of Students/Staff on use of ICT for learning
Activity 1: Identify the software suitable for enhanced students learning | Identify suitable software for enhanced student learning | [13 empty] | Students and Staff using advanced software for their learning/teaching and research |  | 500 |  |  | Centre Management
Activity 2: Identify and engage a suitable resource person | Engage suitable resource persons | Suggest suitable software | [14 empty] | 1000
Activity 3: Organise training | Organise training sessions | Suggest resource persons | [14 empty] | 13000
Action 4: DLI 4: Quality of Education/Research
Sub-Action 4a: CEFTER Thematic Annual Research Grant
Activity 1: Hold planning meetings | Hold meetings to plan and send out call for grant applications | [13 empty] | Annual Grant successfully awarded |  | 500 |  |  | Centre Management
Activity 2: Receive and review grant applications | Review grant applications | Review applications | [14 empty] | 1000
Activity 3: Award grants to successful applicants. Target: 6 | Award grants to applicants that meet the set criteria | [15 empty] | 10000
Sub-Action 4b: Funding peer reviewed publications from CEFTER Staff and Students
Activity 1: Students and faculty publications submitted to CEFTER publications committee | Publications by students and faculty submitted to committee for consideration | [13 empty] | Number of publications published on SCOPUS indexed journals |  |  |  |  | Centre Management
Activity 2: The committee reviews and shortlists good quality publications | Select quality publications | [15 empty] | 1000
Activity 3: Shortlisted publications sent to experts for peer review | Selected publications sent for review | [15 empty] | 1000
Activity 4: Payment of publication charges | Payment of publication charges | [15 empty] | 3000
Activity 5: Subscription to Journals | Subscription to Journals | [15 empty] | 2000
Sub-Action 4c: Procurement of Laboratory Equipment and Consumables
Activity 1: Conduct needs assesment with departments and partners | Get a comprehensive list of equipments and consumables needed | [13 empty] | Students and Staff enjoying facilities procured for research and teaching
Activity 2: Procurement of Consumables | [16 empty] | 2000
Activity 5: Procurement of screens, licences nd softwares | [16 empty] | 3000 |  |  | Centre Management
Sub-Action 4d: Student-Faculty Grant (CPSS)
Activity 1: Students and faculty complete and submit application form | Call for and receive applications for grants from Sudents and Faculty | Submit applications | [12 empty] | Student and Faculty conducting research on approved projects |  |  |  |  | Centre Management
Activity 2: The Scholarship and Grants Committee meets and shortlists candidates for interview | Cosider applications and shortlist candidates for interview | Participate in consideration of applications and shortlisting | [14 empty] | 1000
Activity 3: Shortlisted candidates defend their proposals before the committee | Proposal defence by shortlisted candidates | Proposal defence
Activity 4: Disbursement to 10 successful grant applicants | Successful candidates receive disbursement. Target: 5 | [15 empty] | 10000
Sub-action 4e: Safeguard activities
Activity 1: Conduct ESMP implementation audit | Conduct audits for all construction works on campus. | [15 empty] | 5000
Activity 2: Procure first aid boxes for all production units at CEFTIC | Provide adequate work signage around work area/institution premises. | [15 empty] | 4000
Sub-Action 4f: National Program Accreditation
Activity 1: Undergo national re-accreditation for programs that are due | Certain programs that are due for accreditation will be put up | [15 empty] | 8000
Action 5: DLI 5: Relevance of Education/Research
Sub-Action 5a: Partnership Activities
Activity 2: Implement partnership activities with the University of Zagreb (Research, Technology Transfer, Incubation, and trainings) | Sign specific agreements with faculties and TTO | Organise internships | [12 empty] | List of partnership activities and collaborations |  | 4000
Activity 3: Establish new partnerships with UNHCR, EU and Michigan State University | Establish Partnerships | Jiont activities | [12 empty] | Signed MoUs |  | 10000
Activity 4: Meeting with Food processing industries, National policy makers, and NASENI | Development of policies in the food sector, and an effort to woo agic-related industries to the State | [15 empty] | 5000
Sub-Action 5b: CEFTER Enterprise Development
Activity 1: Follow up on innovation challenge grant award recepients | Follow up on startups that received technical and financial awards | [15 empty] | 500
Activity 2: Developments of Patents and Licencing | Development of patents and licencing | [15 empty] | 2000
Activity 3: Commercialisation of research outputs | Commercialisation of research outputs | [15 empty] | 2000
Sub-Action 5c: Provision of Extension and Community Awarness on Post-Harvest Losses
Activity 1: Update and review database on agricultural produce | Data will be collected from the field extension staff at regular basis to update the database | Participate in meetings | [12 empty] | Members of the Community adopt improved processing and preservation techniques |  | 1000 |  |  | Centre Management
Activity 2: Organise community awareness campaigns | Organise awarenesses campaigns | Engage in campaigns | [14 empty] | 2000 |  |  | CentreManagement
Sub-Action 5d: Student/Staff Internship
Activity 1: Identify Industrial and sectoral Partners for students' internship | Identify the Industries and Sectoral partners that can meet the internship needs | Identify industries and partners
Activity 2: Consider internship areas | Consider the different areas for students internships | Present internship areas | [17 empty] | Centre Management
Activity 3: Develop internship manuals | Develop manuals for internship | Develop manuals | [14 empty] | 1000
Activity 4: Develop Schedule for Student distribution | Prepare a student distribution schedule
Activity 5: Staff Internship | Assign staff to partner institutions to understudy research activities Target 3 | [15 empty] | 5000
Sub-Action 5e: Grant Application:
Activity 1: Hold planning meetings | Hold meetings and consider available grants | Suggest grant winning ideas | [12 empty] | 3 grants applications submitted each year |  | 500 |  |  | Centre Management
Activity 2: Write and apply for grants | Apply for grants | [15 empty] | 500
Activity 3: Hold capacity building on writing for big grants | Engage resource persons to train faculty on application for big grants | Facilitate applications | [14 empty] | 4000
Action 6: DLI 6: Timeliness/Quality of Financial Management
Sub-Action 6a: Regional Project Review Workshops
Activity 1: Identify and notify participants | Identify and notify regional workshop participants | [13 empty] | Management identifying areas of weakness for improvement |  |  |  |  | Centre Management
Activity 2: Prepare update report on project | Prepare update report on project
Activity 3: Submit to CEFTER technical Committee for inputs | Submit report to technical committee for consideration
Activity 4: Travels and accomodation cost | Settle workshop expenses | [15 empty] | 50000
Sub-Action 6b: Internal Monitoring and Evaluation Activities
Activity 1: Conduct review of all CEFTER activities, coordinate the end of project report | Review CEFTER activities quaterly | [15 empty] | 5000 |  |  | M&E team
Sub-Action 6c: Financial Management
Activity 1: Meeting of Audit committee | The audit committee meets to consider financial reports | [15 empty] | 1500 |  |  | Audit Committee
Activity 2: Training of account/audit staff | Account/Audit staff shall attend annual trainings and workshops | [15 empty] | 6000 |  |  | Centre Management
Activity 3: Purchase and update of accounting software | Payment for licences and upgrade of software | [15 empty] | 3000 |  |  | Accounts Unit
Activity 4: External Audit | External audit of financial reports | [15 empty] | 5000 |  |  | External Auditor
Action 7: DLI : Institutional Impact
Sub-Action 7a: Institutional benchmarking activities (PASET)
Activity 1: Continue on implementing activities as outlined in Intervention Plan | [14 empty] | A completed survey indicating progress to the intervention plan and readiness to participate in benchmarking exercise |  | 5000 |  |  | Centre Management
Action 8: Communication
Activity 1: Regular Website updates | The website will carry updated information on all Centre activities including research, trainings, awards, and so on. | [13 empty] | Active website links |  | 2000 |  |  | Centre management, Communications officer
Activity 2: Regular update of social media platforms | [14 empty] | Minimum of 3 posts weekly |  | 1000
Activity 3: Media engagement | Engage mainstream media (radio, televisions, news papers and magazines) to further disseminate centre’s output/ success stories- sharing compelling articles with local and international media. Use community media for grassroots engagement and participation. | [13 empty] | At least 1 mainstream feature quarterly |  | 1000
Activity 4: Production of communication materials- newsletters, brochures, factsheets, infographics, videos, engaging images (photo repository/image bank) | Produce newsletters and magazines. Theatre arts and mass communication departments will be engaged to produce TV and radio jingles that highlight success stories, key activities, and events of the centre in various local languages. They will also be at the forefront of descemination of information. Produce simple communication materials such as brochures and factsheets. | [13 empty] | Production of quarterly newsletters |  | 2000
Activity 5: Produce and Circulate flyers, Posters and Monographs | [16 empty] | 1000
[15 empty] | TOTAL |  | 230000
[16 empty] | Total Estimated Budget ($) | 230000