## General Work Plan
COUNTRY: NIGERIA
PROJECT NAME: AFRICA CENTRES OF EXCELLENCE FOR DEVELOPMENT IMPACT (ACE IMPACT)
CENTRE NAME: CENTRE FOR FOOD TECHNOLOGY AND RESEARCH WORK PLAN (JANUARY - DECEMBER 2025)
Year 2025
Activity No | ACTIVITY | SUB-ACTIVITY | JUSTIFICATION | ESTIMATED BUDGET ($) | REMARKS | RESPONSIBLE UNIT
[7 empty] | January | February | March | April | May | June | July | August | September | October | November | December
1.1 | Regional/National Conference and Seminar by Staff and Students | Activity 1: Collaboration with FOOD4WA on ongoing Regional seminar series | Mainstreaming of improved learning and teaching methods in the institutions | 2000 |  | Centre Management
|  | Activity 2: Sponsorship of staff and students on regional/national/international conference |  | 5000
1.2 | Post-harvest Clinic/activities | Activity 1: Conduct needs assesment to identify Communities for participatory conduct of Post-Harvest Clinic | Community members adopt improved techniques for food preservation and processing |  |  | Centre Management
Activity 2: Draft report for consideration by Technical Committee
|  | Activity 3: Design curriculum and train resource persons from the communities |  | 10000
2.1 | Implementation of modules developed from the training on transportation of foodproduce to market, food handling, processing and preservation | Activity 1: Identify suitable individuals/communities to test run the modules | Use of new modules by farmers/food handlers to improve their income |  |  | Centre Management
|  | Activity 2: Train community members in the use of developed modules |  | 10000
2.2 | Training of Technologist and Laboratory Automation | Activity 1: Identify the new specialised equipment and conduct training | Trained laboratory technologists deployed to the departments | 2000 |  | Centre Management
|  | Activity 2: Payment for softwares, licence subscriptions |  | 8000
2.3 | Training of Students/Staff on use of ICT for learning | Activity 1: Identify the software suitable for enhanced students learning | Students and Staff using advanced software for their learning/teaching and research | 500 |  | Centre Management
|  | Activity 2: Identify and engage a suitable resource person |  | 1000
|  | Activity 3: Organise training |  | 5000
3.1 | CEFTER Thematic Annual Research Grant | Activity 1: Hold planning meetings | Annual Grant successfully awarded | 500 |  | Centre Management
|  | Activity 2: Refurbishing and furnishing of CEFTER Conference Room |  | 25000
|  | Activity 3: Receive and review grant applications |  | 1000
|  | Activity 4: Award grants to successful applicants. Target: 6 |  | 10000
3.2 | Funding Peer Reviewed publications from CEFTER Staff and Students | Activity 1: Students and faculty publications submitted to CEFTER publications committee | Number of publications verified and accepted by Association of African Universities (AAU) monitoring committee |  |  | Centre Management
|  | Activity 2: The committee reviews and shortlists good quality publications |  | 1000
|  | Activity 3: Shortlisted publications sent to experts for peer review |  | 1000
|  | Activity 4: Payment of publication charges |  | 3000
|  | Activity 5: Subscription to Journals |  | 2000
3.3 | Procurement of Laboratory Equipment and Consumables | Activity 1: Conduct needs assesment with departments and partners | Students and Staff enjoying facilities procured for research and teaching |  |  | Centre Management
|  | Activity 2: Procurement of Consumables |  | 2000
|  | Activity 3: Procurement of screens, licences nd softwares |  | 3000
3.4 | Student-Faculty Grant (CPSS) | Activity 1: Students and faculty complete and submit application form | Student and Faculty conducting research on approved projects |  |  | Centre Management
|  | Activity 2: The Scholarship and Grants Committee meets and shortlists candidates for interview |  | 1000
Activity 3: Shortlisted candidates defend their proposals before the committee
|  | Activity 4: Disbursement to 10 successful grant applicants |  | 10000
3.5 | Safeguard activities | Activity 1: Conduct ESMP implementation audit |  | 3000
|  | Activity 2: Procure first aid boxes for all production units at CEFTIC |  | 4000
3.6 | National Program Accreditation | Activity 1: Undergo national re-accreditation for programs that are due |  | 8000
4.1 | Partnership Activities | Activity 2: Implement partnership activities with the University of Zagreb (Research, Technology Transfer, Incubation, and trainings) | List of partnership activities and collaborations | 4000 |  | Centre Management
|  | Activity 3: Establish new partnerships with UNHCR, EU and US Institutions | Signed MoUs | 10000
|  | Activity 4: Meeting with Food processing industries, National policy makers. |  | 5000
4.2 | CEFTER Enterprise Development | Activity 1: Follow up on innovation challenge grant award recepients | One startup per year | 500 |  | TTO
|  | Activity 2: Developments of Patents and Licencing |  | 2000
|  | Activity 3: Commercialisation of research outputs |  | 2000
4.3 | Provision of Extension and Community Awarness on Post-Harvest Losses | Activity 1: Update and review database on agricultural produce | Members of the Community adopt improved processing and preservation techniques | 1000 |  | Centre Management and Partners
|  | Activity 2: Organise community awareness campaigns |  | 2000
4.4 | Student/Staff Internship | Activity 1: Identify Industrial and sectoral Partners for students' internship |  |  |  | Centre Management
Activity 2: Consider internship areas
|  | Activity 3: Develop internship manuals |  | 1000
Activity 4: Develop Schedule for Student distribution
|  | Activity 5: Staff Internship |  | 5000
4.5 | Grant Application: | Activity 1: Hold planning meetings | 3 grants applications submitted each year | 500 |  | Centre Management
|  | Activity 2: Write and apply for grants |  | 500
|  | Activity 3: Hold capacity building on writing for big grants |  | 4000
5.1 | Regional Project Review Workshops | Activity 1: Identify and notify participants | Management identifying areas of weakness for improvement |  |  | Centre Management
Activity 2: Prepare update report on project
Activity 3: Submit to CEFTER technical Committee for inputs
|  | Activity 4: Travels and accomodation cost |  | 40000
5.2 | Internal Monitoring and Evaluation Activities | Activity 1: Conduct quaterly review of all CEFTER activities to ensure they meet desired quality and deadlines |  | 2000 |  | M&E team
5.4 | Financial Management | Activity 1: Meeting of Audit committee |  | 1500 |  | Audit Committee
|  | Activity 2: Training of account/audit staff |  | 6000 |  | Centre Management
|  | Activity 3: Purchace and update of accounting software |  | 3000 |  | Accounts Unit
|  | Activity 4: External Audit |  | 3000 |  | External Auditor
6.1 | Institutional benchmarking activities (PASET) | Activity 1: Meeting milestones for promoting institutional Impact as outlined in Implimentation Plan | A completed survey indicating progress to the intervention plan and readiness to participate in benchmarking exercise | 5000 |  | Centre Management
7.1 | Communication | Activity 1: Regular Website updates | Active website links | 2000
|  | Activity 2: Regular update of social media platforms | Minimum of 3 posts weekly | 1000
|  | Activity 3: Online repository for research outputs | Visible page/ tab on centre’s website outlining the various research undertaken by the centre. | 1000
|  | Activity 4: Media engagement | At least 1 mainstream feature quarterly | 2000
|  | Activity 5: Production of communication materials- newsletters, brochures, factsheets, infographics, videos, engaging images (photo repository/image bank) | Production of quarterly/ bi-annual newsletters | 1000
| Total |  |  | 223000
| Operating Expenses 10% |  |  | 22300
| Grand Total |  |  | 245300

## Procurement Plan Works
COUNTRY: NIGERIA
PROJECT: AFRICA CENTRES OF EXCELLENCE FOR DEVELOPMENT IMPACT (ACE IMPACT)
Loan No
NAME OF INSTITUTION: BENUE STATE UNIVERSITY MAKURDI
WORKS | [8 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
|  |  | BASIC DATA | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  |  | Contract Implementation
S/NO. | Description* | Package Number | Lot Number | Estimated Amount in US $ | Procurement Method | Pre-or Post Qualification | Prior or Post Review | Plan vs. Actual | Prep & Submission by Ex Agency | No-objection Date | On-line UNDB Gateway Nat Press | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount in US$ | Date Contract Award | Date Contract Advert | Date Contract Signature | Opening of Let of Credit | Arrival of Goods
| Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | Plan | 4 - 7 wks | 1 - 1.5 wks | 1.5 - 2 wks | 6 to | 12 wks | 1.5 - 3 wks | 1 - 1.5 wks | Plan |  | 1 wk |  | 1.5-3 wks
[6 empty] | add 7-13 wks |  | Actual | [7 empty] | Actual
WORKS
NONE |  |  |  |  | RFB | Post Qualification | N\A |  | N\A | N\A | N\A | 6th-Jan-25 | 2025-01-10 | 25th-Jan-25 | N\A |  | 0 | 2025-01-30 | N\A | 2025-02-10 | N\A | 2025-02-20
[5 empty] | RFQ | Post Qualification | N\A |  | N\A | N\A | N\A | 6th -Jan-25 | 2025-01-10 | 25th-Jan-25 | N\A |  | 0 | 2025-01-30 | N\A | 2025-02-10 | N\A | 2025-02-20
| Total Cost |  |  | 0 | [12 empty] | 0
| Fill gray cells only! |  |  | EXCHANGE RATE: ₦1500= U.S. $1.00

## Procurement Plan Goods
COUNTRY: NIGERIA
PROJECT: AFRICA CENTRES OF EXCELLENCE FOR DEVELOPMENT IMPACT (ACE IMPACT)
Loan No
NAME OF INSTITUTION: BENUE STATE UNIVERSITY MAKURDI
GOODS | [8 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
|  |  | BASIC DATA | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  |  | Contract Implementation
S/NO. | Description* | Package Number | Lot Number | Estimated Amount in US $ | Procurement Method | Pre-or Post Qualification | Prior or Post Review | Plan vs. Actual | Prep & Submission by Ex Agency | No-objection Date | On-line UNDB Gateway Nat Press | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount in US$ | Date Contract Award | Date Contract Advert | Date Contract Signature | Opening of Let of Credit | Arrival of Goods | Inspection Final Acceptance
| Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | Plan | 4 - 7 wks | 1 - 1.5 wks | 1.5 - 2 wks | 6 to | 12 wks | 1.5 - 3 wks | 1 - 1.5 wks | Plan |  | 1 wk |  | 1.5-3 wks
[6 empty] | add 7-13 wks |  | Actual | [7 empty] | Actual
GOODS
1 | Refurbishing and furnishing of CEFTER Conference Room |  |  | 25000 | RFQ | Post Qualification | Post Review |  |  | NA |  | 2025-02-06 | 2025-02-10 | 2025-02-20 | NA |  | 25000 | 2025-02-20 |  | 2025-04-10 |  | 2025-03-20
2 | Procurement of Consumables |  |  | 2000 | RFQ | Post Qualification | Post Review |  |  | NA |  | 2025-02-06 | 2025-02-20 | 2025-02-17 | NA |  | 2000 | 2025-03-24 |  | 2025-04-05 |  | 2025-04-29
| Procurement of screens, licences nd softwares |  |  | 3000 | RFQ | Post Qualification | Post Review |  |  | NA |  | 2025-02-06 | 2025-02-20 | 2025-02-17 | NA |  | 3000 | 2025-03-24 |  | 2025-04-05 |  | 2025-04-29
| Procure first aid boxes for all production units at CEFTIC. |  |  | 4000 | RFQ | Post Qualification | Post Review |  |  | NA |  | 2025-02-06 | 2025-02-20 | 2025-02-17 | NA |  | 4000 | 2025-03-24 |  | 2025-04-05 |  | 2025-04-29
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
| Total Cost |  |  | 34000 | [12 empty] | 34000
| Fill gray cells only! |  |  | EXCHANGE RATE: ₦1500= U.S. $1.00

## Procurement Plan Consultancy
COUNTRY: NIGERIA
PROJECT: AFRICA CENTRES OF EXCELLENCE FOR DEVELOPMENT IMPACT (ACE IMPACT)
CREDIT NO:
NAME OF INSTITUTION: BENUE STATE UNIVERSITY MAKURDI
For Contracts under projects approved before the May 2002 Guidelines
|  |  | If Post-Review, No-objection Dates are not needed | [5 empty] | Request for EOI (where required)
CONSULTANCY |  |  | Contract Type |  |  |  | Preparation Request for Proposals |  |  |  | Short List |  |  | Consultant Proposals |  | Proposal Evaluation and Negotiation for Projects after May 2002 Technical (T) & Financial (F) and Negotions (N) | [5 empty] | Draft Contract |  | Contract Finalization |  |  |  |  | Contract Implementation
S/No. | Description* | Selection Method | Lumpsum or Time-Based | Estimated Amount in US$ '000 | Prior/Post Review | Plan vs. Actual | Prep & Submission by Ex Ag | No-objection Date | On-line UNDB Gateway Nat Press | Lead-time before shortlist | Submission Date | No-objection Date | Plan vs. Actual | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | No-objection Evaluation Report (T) | Opening Financial Proposals | Preparation Eval Report (T) (F) | Negotiations (N) | Plan vs. Actual | Submission Date | No-objection Date | Contract Amount in US$ '000 | Contract Award | Date Contract Advert | Contract Signature | Plan vs. Actual | Mobilization Advance Payment | Draft Report | Final Report | Final Cost US$ '000
| Norm Duration of Proc Steps |  |  |  |  | Plan | 3 - 6 wks | 1 - 2 wks | 1 - 1.5 wks | 2 wks |  | 1 - 2 wks | Plan | 4 to | 12 wks | 2 - 3 wks | 0.5 - 2 wks | 2 wks | 1 - 2 wks | 2 wks | Plan | 1 - 2 wks | 1 - 2 wks |  | 1 wk |  | 1 - 3 wks | Plan
[6 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
List of Contracts
1 | Conduct ESMP implementation audit | QCBS |  | 3000 | Prior R | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
|  | DIR | TIME BASE |  |  | Actual | [6 empty] | Actual | 2025-01-07 | 2025-01-13 | 2025-02-05 | NA | NA |  |  | Actual |  | NA | 3000 | 10th-Febuary-2025 | NA | 10th-Febuary-2025 | Actual |  |  |  | 3000
2 |  | PPP |  |  |  | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
|  | PPP | TIME BASE |  | Prior R | Actual |  | NA | NA | NA |  |  | Actual | NA | NA | NA |  |  |  |  | Actual | NA | NA |  |  | NA |  | Actual |  |  |  | 0
| TOTAL AMOUNT |  |  | 3000 |  | Plan | [6 empty] | Plan | [7 empty] | Plan |  |  | 3000 |  |  |  | Plan |  |  |  | 3000
[6 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual

## Procurement Plan Training
COUNTRY: NIGERIA
PROJECT: AFRICA CENTRES OF EXCELLENCE FOR DEVELOPMENT IMPACT (ACE IMPACT)
CREDIT NO: IDA
NAME OF INSTITUTION: BENUE STATE UNIVERSITY MAKURDI
TRAINING/CAPACITY BUILDING
S/N | DESCRIPTION | NAMES OF PARTICIPANTS | OBJECTIVES | OUTCOME | TRAINING LOCATION | COST
1 | Training of Technologist and Laboratory on specilized equipment | Laboratory and Technologist staff | Generation of high quality technologist and laboratory automation personnel | Curricula for innovative University teaching developed |  | 10000
3 | Training of Students/Staff on use of ICT for learning | staff/students | Students benefitting from new innovative teaching methods. Increase in number of faculty using innovative teaching methods | Qualified candidates identified |  | 6500
[5 empty] | TOTAL | 16500

## Disbursement Plan
COUNTRY: NIGERIA
PROJECT: AFRICA CENTRES OF EXCELLENCE FOR DEVELOPMENT IMPACT (ACE IMPACT)
CENTRE: CENTRE FOR FOOD TECHNOLOGY AND RESEARCH
CREDIT NO: IDA
DISBURSEMENT PLAN (JANURY - DECEMBER, 2025)
S/N | ACTIVITIES | OBJECTIVE | AMOUNT | MONTHS
|  |  | $ | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | TOTAL
GOODS
1 |  | Refurbishing and furnishing of CEFTER Conference Room | AMOUNT $: 25000; MONTHS FEB: 10000; MONTHS MAR: 15000; MONTHS TOTAL: 25000
2 |  | Procurement of Consumables | AMOUNT $: 2000; MONTHS FEB: 2000; MONTHS TOTAL: 2000
3 |  | Procurement of screens, licences nd softwares | AMOUNT $: 3000; MONTHS MAR: 3000; MONTHS TOTAL: 3000
4 |  | Procure first aid boxes for all production units at CEFTIC | AMOUNT $: 4000; MONTHS FEB: 2000; MONTHS MAR: 2000; MONTHS TOTAL: 4000
5 |  |  | MONTHS TOTAL: 0
TRAINING
1 |  | Training of Technologist and Laboratory Automation | AMOUNT $: 10000; MONTHS JAN: 2000; MONTHS FEB: 2000; MONTHS MAR: 3000; MONTHS APR: 3000; MONTHS TOTAL: 10000
2 |  | Training of Students/Staff on use of ICT for learning | AMOUNT $: 6500; MONTHS JAN: 500; MONTHS FEB: 2000; MONTHS MAR: 2000; MONTHS APR: 2000; MONTHS TOTAL: 6500
3 |  |  | MONTHS TOTAL: 0
4 |  |  | MONTHS TOTAL: 0
CONSULTANCIES
1 |  | Conduct ESMP implementation audit | AMOUNT $: 3000; MONTHS APR: 3000; MONTHS TOTAL: 3000
2 |  |  | MONTHS TOTAL: 0
3 |  |  | MONTHS TOTAL: 0
4 |  |  | MONTHS TOTAL: 0
5 |  |  | MONTHS TOTAL: 0
6 |  |  | MONTHS TOTAL: 0
OPERATING COST
1 |  | Regional/National Conference and Seminar by Staff and Students | AMOUNT $: 7000; MONTHS FEB: 2000; MONTHS MAR: 5000; MONTHS TOTAL: 7000
2 |  | Post-harvest Clinic/activities | AMOUNT $: 10000; MONTHS MAR: 5000; MONTHS APR: 5000; MONTHS TOTAL: 10000
3 |  | Implementation of modules developed from the training on transportation of foodproduce to market, food handling, processing and preservation | AMOUNT $: 10000; MONTHS MAR: 5000; MONTHS APR: 5000; MONTHS TOTAL: 10000
4 |  | CEFTER Thematic Annual Research Grant | AMOUNT $: 11500; MONTHS JAN: 500; MONTHS FEB: 1000; MONTHS MAR: 5000; MONTHS APR: 5000; MONTHS TOTAL: 11500
5 |  | Funding Peer Reviewed publications from CEFTER Staff and Students | AMOUNT $: 7000; MONTHS JAN: 1000; MONTHS FEB: 1000; MONTHS MAR: 3000; MONTHS APR: 2000; MONTHS TOTAL: 7000
6 |  | Student-Faculty Grant (CPSS) | AMOUNT $: 11000; MONTHS JAN: 1000; MONTHS APR: 10000; MONTHS TOTAL: 11000
7 |  | National Program Accreditation | AMOUNT $: 8000; MONTHS FEB: 8000; MONTHS TOTAL: 8000
8 |  | Partnership Activities | AMOUNT $: 19000; MONTHS FEB: 4000; MONTHS MAR: 10000; MONTHS APR: 5000; MONTHS TOTAL: 19000
9 |  | CEFTER Enterprise Development | AMOUNT $: 4500; MONTHS JAN: 500; MONTHS FEB: 2000; MONTHS MAR: 2000; MONTHS TOTAL: 4500
10 |  | Provision of Extension and Community Awarness on Post-Harvest Losses | AMOUNT $: 3000; MONTHS FEB: 1000; MONTHS MAR: 2000; MONTHS TOTAL: 3000
11 |  | Student/Staff Internship | AMOUNT $: 6000; MONTHS MAR: 1000; MONTHS APR: 5000; MONTHS TOTAL: 6000
12 |  | Grant Application: | AMOUNT $: 5000; MONTHS JAN: 500; MONTHS FEB: 500; MONTHS MAR: 4000; MONTHS TOTAL: 5000
13 |  | Regional Project Review Workshops | AMOUNT $: 40000; MONTHS MAR: 40000; MONTHS TOTAL: 40000
14 |  | Internal Monitoring and Evaluation Activities | AMOUNT $: 2000; MONTHS MAR: 1000; MONTHS APR: 1000; MONTHS TOTAL: 2000
15 |  | Financial Management | AMOUNT $: 13500; MONTHS JAN: 1500; MONTHS FEB: 6000; MONTHS MAR: 3000; MONTHS APR: 3000; MONTHS TOTAL: 13500
16 |  | Institutional benchmarking (PASET) | AMOUNT $: 5000; MONTHS JAN: 1000; MONTHS FEB: 1000; MONTHS MAR: 1000; MONTHS APR: 2000; MONTHS TOTAL: 5000
17 |  | Communication | AMOUNT $: 7000; MONTHS JAN: 3000; MONTHS FEB: 1000; MONTHS MAR: 2000; MONTHS APR: 1000; MONTHS TOTAL: 7000
18 |  |  | MONTHS TOTAL: 0
19 |  |  | MONTHS TOTAL: 0
20 |  |  | MONTHS TOTAL: 0
21 |  |  | MONTHS TOTAL: 0
22 |  |  | MONTHS TOTAL: 0
23 |  |  | MONTHS TOTAL: 0
24 |  |  | MONTHS TOTAL: 0
25 |  |  | MONTHS TOTAL: 0
26 |  |  | MONTHS TOTAL: 0
27 |  |  | MONTHS TOTAL: 0
28 |  |  | MONTHS TOTAL: 0
| TOTAL |  | 223000 | 11500 | 45500 | 114000 | 52000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 223000