## Sheet1
Name of Center: Center for Food Technology and Research (CEFTER)
Institution: Benue State University |  |  |  | On Schedule
Country: Nigeria
Center Leader: Dr. Barnabas Achakpa Ikyo |  |  |  | Behind Schedule
Annual Workplan (January-December, 2022)
Work Plan Activities | Description | Partner Contribution (if relevant) | 2022 Y2Q1 |  |  | 2022 Y2Q2 |  |  | 2022 Y2Q3 |  |  | 2022 Y2Q4 |  |  | Milestone/Output | If NEW, Provide Justification | Estimated Budget($) | Estimated Revenue ($) | Contribution from Partner ($) | Person Responsible
|  |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Action 1: DLI 1 Institutional Readine
Sub-Action 1a: Review of existing curricula for relevant PhD programs
Activity 1: Conduct needs assesment | Consider Programs that need to be reviewed | [13 empty] | Students admitted into PhD programs that have been reviewed |  | 2500 |  |  | Departments, Faculty, Postgraduate School
Activity 2: Draft needs assessment for consideration by Technical Committee | List of programs presented for consideration | [15 empty] | 2500
Activity 3: Organise Stakeholders' workshop to review curricula | Invite representatives from the Department involved, Faculty and Postgraduate school for the review | Engage a team of experts in curriculum review | [14 empty] | 20000
Sub-Action 1b: Review of existing curricula for relevant MSc programs
Activity 1: Conduct needs assesment | Consider Programs that need to be reviewed | [13 empty] | Students admitted into MSc programs that have been reviewed |  | 2500 |  |  | Departments, Faculty, Postgraduate School
Activity 2: Draft needs assessment for consideration by Technical Committee | list of programs presented for consideration | [15 empty] | 2500
Activity 3: Organise Stakeholders' workshop to review curricula | Invite representatives from the Department involved, Faculty and Postgraduate school for the review | Engage a team of experts in curriculum review | [14 empty] | 20000
Action 2: DLI 2: Development Impact
Sub-Action 2a: Second West and Central Africa Post Harvest Congress
Activity 1: Hold Planning Meetings | Hold a meeting to assign responsibilities and set up committees | Participate in meetings, share responsibilities | [12 empty] | Congress successfully planned, venue located and paid for |  | 20000 |  |  | Centre Management
Activity 2: Stakehoder Drive | Consider possible stakeholders and inform them | Suggest stakeholders | [14 empty] | 20000
Activity 3: Venue | Get a venue for the congress and pay for it | [15 empty] | 15000
Activity 4: Feeding at the Congress | Participants at the congress will be given at least two meals per day | [15 empty] | 10000
Activity 5: Conference bags and other materials | Writing materials and souvinirs | [15 empty] | 5000
Activity 6: Travels(Local and International) | [16 empty] | 40000
Sub-Action 2b: Participation at Regional Conferences and Seminar by Staff and Students (Estimated Target - 20 Participants)
Activity 1: Conduct needs assesment | Consider requests for regional conference attendance by Staff and students | [13 empty] | Mainstreaming of improved learning and teaching methods in the institutions |  | 2500 |  |  | Centre Management
Activity 2: Travel and accommodation cost for staff and students at regional Conferences | For those approved, provide for the expenses involved | [15 empty] | 15000
Activity 3: Prepare report/proceedings and circulate | Reports submitted by staff and students on return from regional conference will be put together and circulated | [15 empty] | 2500
Sub-Action 2c: National Conference and Seminar by Staff and Students (Estimated Target - 2 Conferences)
Activity 1: Conduct needs assesment | Hold a meeting to consider modalities towards a national conference and seminar for Staff and Students | [13 empty] | Mainstreaming of improved learning and teaching methods in the institutions |  | 1250 |  |  | Centre Management
Activity 2: Organise national stakeholder workshop | Organise workshop for staff and students to come together and discuss problems of teaching, learning and research | [15 empty] | 7500 | 1500
Activity 3: Prepare report/proceedings and circulate | Prepare report/proceeding of the workshop and circulate | [15 empty] | 1250
Sub-Action 2d: Produce and Circulate flyers, Posters and Monographs
Activity 1: Conduct needs assesment | Consider contents and type of the documents to be published | [13 empty] | Flyers, Posters and Monographs in circulation |  | 2000 |  |  | Centre Management
Activity 2: Prepare report and submit to Technical committee for consideration | Presents considerations to the Technical committee | [15 empty] | 1000
Activity 3: Set up an editorial unit and print approved quantity of fliers | Set up editorial unit to produce appoved items | [15 empty] | 12000 | 2400
Sub-Action 2e: National/Regional Post-harvest Clinic/activities
Activity 1: Conduct needs assesment | Consider improved techniques for food preservation and processing | Suggest new techniques | [12 empty] | Community members adopt improved techniques for food preservation and processing |  | 4000 |  |  | Centre Management
Activity 2: Draft report for consideration by Technical Committee | Present considerations to technical committee for | [15 empty] | 1000
Activity 3: Identify Communities for participatory conduct of Post-Harvest Clinic | Consider the target prticipants from Regional and National communities for the Clinic | Make suggestions | [14 empty] | 5000
Activity 4: Design curriculum and train resource persons from the communities | Training of persons from different communities on post-harvest activities | Participate in trainings | [14 empty] | 10000
Action 3: DLI 3: Quantity of Students
Sub-Action 3a: Training of Farmers/Food handlers on safe hygiene and Transportation of Produce to Markets (Estimated Target - 50 Trainees)
Activity 1: Conduct needs assesment | Hold a meeting to set out modalities for the training | Participate in meetings | [12 empty] | Use of new modules by farmers/food handlers to improve their income |  | 500 |  |  | Centre Management
Activity 2: Prepare report and submit to Technical committee for consideration | Draft a report for the training and submit to Technical Committee | [15 empty] | 500
Activity 3: Organise Stakeholders' workshop for industries and local fabricators | Organise Stakeholders' workshop | Participate in workshop | [14 empty] | 3000
Activity 4: Identify suitable modules for safe transportation of fruits and vegetables, grains, roots and tubers | Identify modules that are suitable for the training | Suggest modules | [14 empty] | 500
Activity 5: Identify suitable communities to test run the modules | List out communities in which the modules will be tested | Suggest communities | [14 empty] | 500
Activity 6: Train community members in the use of developed modules | Community members will be trained in the use of the modules | Participate in trainings | [14 empty] | 5000 | 1000
Sub-Action 3b: Training of Faculty in Innovative University Teaching (Estimated Target - 60 Faculty)
Activity 1: Conduct needs assesment | Hold meeting to outline training modalities | Join meetings | [12 empty] | Increase in number of faculty using innovative teaching methods, students benefiting from new innovative teaching methods |  | 2000 |  |  | Centre Management
Activity 2: Draft needs assessment report for consideration by Technical Committee | Submit draft to Technical committee for consideration | [15 empty] | 1000
Activity 3: Organise Trainer of Trainers Workshop involving new partners in innovative teaching and supervision | Train the Trainers on innovative University teaching | Conduct trainings | [14 empty] | 6000
Activity 4: Mobilise partners for cascade training and mainstreaming innovative teaching methods in institutions and schools | The Trainers disseminate knowledge acquired in institutions and schools | [15 empty] | 11000
Sub-Action 3c: Implementation of Short Term Courses(Including Online) (Estimated Target - 30 students)
Activity 1: Conduct needs assesment to identify three to four countries in West and Central Africa for training | Identify Countries in West and Central Africa for the training | Make suggestions | [12 empty] | Graduates from short term courses employed or establishing businesses |  | 10000 |  |  | Centre Management
Activity 2: Develop a suitable curriculum for training. Train resource persons in country and identify trainees | Identify trainees and train resource persons using a suitable curriculum | Suggest trainees | [14 empty] | 10000
Activity 3: Develop program and implement | Implement the short courses | Implement short courses | [14 empty] | 20000 | 4000
Sub-Action 3d: Training of Technologist and Laboratory Automation (Estimated Target - 15 Technologists)
Activity 1: Conduct needs assesment to identify the areas of need | Identify the areas that require training of technologists | [13 empty] | Trained laboratory technologists deployed to the departments |  | 5000 |  |  | Centre Management
Activity 2: Conduct survey to identify national and international institutions with best training facilities | Consider available institutions with the best training facilities nationally and internationally | [15 empty] | 2000
Activity 3: Identify and send suitable candidates for training | Send candidates for training | Conduct trainings | [14 empty] | 33000
Sub-Action 3e: Student Recruitment. (Estimated Target - 70 PhD and MSc Students)
Activity 1: Advertise Senate approved programs on CEFTER website | Place application advert for on CEFTER website | [13 empty] | Students register and resume lectures |  | 2500 |  |  | Centre Management
Activity 2: Advertise Senate approved programs on local and regional print media | Advertise programs on local, regional and print media | [15 empty] | 12500
Activity 3: Technical committee meets to consider shortlisted candidates for admission | Shortlisting of qualified candidates for admission | [15 empty] | 2500
Activity 4: Postgraduate Board meets and approves admission list | Approval of admission list | [15 empty] | 2500
Sub-Action 3f: Student Support/Scholarships (Estimated Target - 40 Student Awards)
Activity 1: Conduct needs assesment | Call for applications for Student Support/Scholarship | [13 empty] | Students receive support/scholarship letters |  | 5000 |  |  | Centre Management
Activity 2: Students Complete application forms seeking for support/scholarship | Interested applicants apply for Support/Scholarship
Activity 3: CEFTER Scholarship and Grants Allocation Committee meets to Shortlist qualified students | Qualified students shortlisted for the award | [15 empty] | 5000
Activity 4: Shortlisted students forwarded to the Vice Chancellor for Approval | Vice Chancellor considers the list for approval
Activity 5: Funding for scholarship awarded to students annually. Covers tuition, accommodation and living expensis | Award of Support/scholarship | [15 empty] | 120000
Sub-Action 3g: Setup of Phd Offices
Activity 1: Design of PhD offices | Design offices for PhD students | [13 empty] | Furnished offices available for PhD students |  | 5000 |  |  | Centre Management
Activity 2: Furnishing of the offices | Furnish offices | [15 empty] | 45000
Sub-Action 3h: Training of Students/Staff on use of ICT for learning (Estimated Target - 50 Trainees)
Activity 1: Conduct needs assessment | Conduct needs assessment | [13 empty] | Students and Staff using advanced software for their learning/teaching and research |  | 500 |  |  | Centre Management
Activity 2: Identify the software suitable for enhanced students learning | Identify suitable software for enhanced student learning | Suggest suitable software | [14 empty] | 500
Activity 3: Identify and engage a suitable resource person | Engage suitable resource persons | Suggest resource persons | [14 empty] | 1000
Activity 4: Organise training | Organise training sessions | [15 empty] | 13000
Action 4: DLI 4: Quality of Education/Research
Sub-Action 4a: CEFTER Thematic Annual Research Grant
Activity 1: Hold planning meetings | Hold meetings to plan and send out call for grant applications | [13 empty] | Annual Grant successfully awarded |  | 10000 |  |  | Centre Management
Activity 2: Receive and review applications | Review received applications | Review applications | [14 empty] | 5000
Activity 3: Award grants | Award grants to application that meet the set criteria | [15 empty] | 35000
Sub-Action 4b: Funding peer reviewed publications from CEFTER Staff and Students (Estimated Target - 25 funded Publications)
Activity 1: Students and faculty publications submitted to CEFTER publications committee | Publications by students and faculty submitted to committee for consideration | [13 empty] | Number of publications verified and accepted by Association of African Universities (AAU) monitoring committee |  |  |  |  | Centre Management
Activity 2: The committee reviews and shortlists good quality publications | Good quality publications are selected | [15 empty] | 1000
Activity 3: Shortlisted publications sent to experts for peer review | Selected publications sent for review | [15 empty] | 1000
Activity 4: Payment of publication charges | Payment of publication charges | [15 empty] | 4000
Activity 5: Subscription to Journals | Subscription to Journals | [15 empty] | 4000
Sub-Action 4c: Construction of CEFTER Food Technology Innovation Complex (CEFTIC)
Activity 1: Award contract | Contract awarded for construction and installation
Activity 2: Construction of complex | Contract awarded for construction and installation | [15 empty] | 1100000
Sub-Action 4d: Procurement of Small Equipment and Consumables
Activity 1: Conduct needs assesment with departments and partners | Get a comprehensive list of equipments and consumables needed | [13 empty] | Students and Staff enjoying facilities procured for research and teaching |  |  |  |  | Centre Management
Activity 2: Draft report for consideration | Consider report
Activity 3: Submit Proposal to procurement committee | Submit proposal to procurement committee
Activity 4: Advertise for tenders | Advertise for tenders | [16 empty] | 1600
Activity 5: Contract awarded for purchase and installation (GCMS for Chemistry lab, FITR Spectrometer, Software and informatics) | Award contract | [15 empty] | 150000
Sub-Action 4e: Installation of 50Kva Solar Power to the new CEFTER Complex
Activity 1: Advertise for tenders | Advertise for tenders | [15 empty] | 25000 | 5000
Activity 2: Contract awarded for purchase and installation of Solar panels, Batteries, Inverters and smart grid system | Award contract | [15 empty] | 85000
Sub-Action 4f: Provision of Water supply at the new CEFTER Complex
Activity 1: Conduct needs assesment and Draft report for consideration | Hold meeting to consider and prepare a report | [13 empty] | Available steady water supply at the office complex and in the hostels |  | 1000 |  |  | Centre Management
Activity 2: Submit Proposal to procurement committee | Procurement committee consider proposal
Activity 3: Advertise for tenders | Advertise for tenders | [16 empty] | 5000
Activity 4: Contract awarded | Award contract | [15 empty] | 40000
Sub-Action 4g: Furnishing of Refurbished Stdents Hostel
Activity 1: Conduct needs assesment and Draft report for consideration | Get a comprehensive list of needed furnitures and fittings | [16 empty] | 5000 |  | Centre Management
Activity 2: Contract awarded for purchase of furnitures and installation of fittings | Award contract | [13 empty] | Hostel, well furnished and allocated to students |  | 150000
Sub-Action 4h: Student-Faculty Grant (CPSS) (Estimated Target - 10 Grant Awards)
Activity 1: Students and faculty complete and submit application form | Call for and receive applications for grants from Sudents and Faculty | Submit applications | [12 empty] | Student and Faculty conducting research on approved projects |  |  |  |  | Centre Management
Activity 2: The Scholarship and Grants Committee meets and shortlists candidates for interview | Cosider applications and shortlist candidates for interview | Participate in consideration of applications and shortlisting | [14 empty] | 2500
Activity 3: Shortlisted candidates defend their proposals before the committee | Proposal defence by shortlisted candidates | Proposal defence | [14 empty] | 2500
Activity 4: Disbursement to successful grant applicants | Successful candidates receive disbursement | [15 empty] | 25000
Activity 5: Special research grants | Successful candidates receive disbursement | [15 empty] | 25000
Sub-Action 4i: Establishment of Regional Research Groups
Activity 1: Conduct needs assesment for establishment of regional working groups | Hold meetings to consider the available networking options and advantages | Participate in meetings | [12 empty] | Joint publications in high quality Journals |  | 4000 |  |  | Centre Management, Regional Partners, Heads of Departments
Activity 2: Organise a regional faculty stakeholders workshop to formation of regional working groups and how to network | Organise workshops to form regional groups and consider networking options | Participate in workshops | [14 empty] | 14000
Activity 3: Draft reports and share | Draft and share reports | [15 empty] | 2000
Action 5: DLI 5: Relevance of Education/Research
Sub-Action 5a: Partnership Activities
Activity 1: Training of Staff at MSc, PhD levels: Study fellowship | Staff considered for study fellowship | Train Staff at MSc and PhD levels | [12 empty] | Completion of agreed activities for each quater |  | 80000 |  |  | Project Technical Committee
Activity 2: Student Internships (This includes accomodation, monthly stipend, transport, supervision and consumables) | Students engaged on internships | Organise internships | [14 empty] | 80000
Activity 3: Joint Projects | Joint activities with partners | Jiont activities | [14 empty] | 50000
Activity 4: Short courses training: Local and international travels | Local and international participation in short courses | Participation in short courses | [14 empty] | 70000 | 14000
Activity 5: Refurbishing of partnership offices | Renovation and furnishing of some partnership offices | [15 empty] | 40000
Sub-Action 5b: Faculty and Students Food Post-harvest Week
Activity 1: Conduct needs assesment | Formulate student groups | [13 empty] | Students and Entrepreneurs establish businesses using processed food products. Successful patentingof some food products |  | 1000 |  |  | Centre Management
Activity 2: Identify crops and assign to students groups | Assign specific crops to student groups | [15 empty] | 1000
Activity 3: Assign faculty to student groups as mentor | Assign faculty to each student group to serve as mentor | [15 empty] | 1000
Activity 4: Student identify food products and prepare budgets | Students prepare and submit budgets | [15 empty] | 8000
Activity 5: Funding | Funds released for raw materials and accessories for the food week | [15 empty] | 14000
Sub-Action 5c: CEFTER Enterprise Development
Activity 1: Hold planning meetings | Call for applications on enterprise development | [13 empty] | One startup per year |  | 10000 |  |  | Centre Management
Activity 2: Receive and review applications | Review submitted applications | Review applications | [14 empty] | 15000
Activity 3: Setup small and medium scale Funding for three year start-ups per year. 3 winning groups in the enterprise competition will use the fund to set up an agro based small scale enterprise | Consider successful applications for small and medium scale funding for start-ups | Consider applications | [14 empty] | 75000
Sub-Action 5d: Provision of Extension and Community Awarness on Post-Harvest Losses
Activity 1: conduct needs assesment | Draft out report on community awareness process | Participate in meetings | [12 empty] | Members of the Community adopt improved processing and preservation techniques |  | 1000 |  |  | Centre Management
Activity 2: Prepare report and submit to Technical Committee for consideration | Submit report for consideration | Consider report | [14 empty] | 1000
Activity 3: Prepare a report on level of post-harvest losses accross crop value chain in West and central Africa | Project the level of post harvest losses across West and Central Africa | [15 empty] | 3000
Activity 4: Organise yearly community awareness campaigns in selected countries in West and Central Africa | Organise awarenesses campaigns | Engage in campaigns | [14 empty] | 10000 |  |  | CentreManagement
Activity 5: Set up of West African agricultural extension service network | Create networks for agricultual extension services | Suggest specific areas and locations | [14 empty] | 10000 |  |  | and Partners
Sub-Action 5e: Student Intership (Estimated Target - 75 students)
Activity 1: Conduct needs assesment | Consider the different areas for students internships | Present internship areas | [12 empty] | Students deployed to institutions for internship |  | 2000 |  |  | Centre Management
Activity 2: Identify Industrial and sectoral Partners for students' internship | Identify the Industries and Sectoral partners that can meet the internship needs | Identify industries and partners
Activity 3: Develop internship manuals | Develop manuals for internship | Develop manuals | [14 empty] | 1000
Activity 4: Develop Schedule for Student distribution | Prepare a student distribution schedule | [15 empty] | 12000
Activity Payment of intern service charges at industrial site | Prepare a student distribution schedule | [15 empty] | 45000
Sub-Action 5f: Setup and maintenance of graduate Tracking System
Activity 1: Hold planning meetings | Plan on the modalities for setting up a graduate tracking system | [13 empty] | Tracking of CEFTER graduates from 2016 -2019 |  | 1000 |  |  | Centre Management
Activity 2: Development and hosting of graduate tracking system online | Develop an online graduate tracking system | [15 empty] | 5000
Activity 3: Salary for 2 staff in the graduate tracking unit | Payment of staff involved | [15 empty] | 9000
Sub-Action 5g: Fund Raising Activities
Activity 1: Conduct needs assesment | Conduct needs assessment | [13 empty] | The project achieves up to 100% of IGR |  |  |  |  | Centre Management
Activity 2: Prepare report and submit to Technical Committee | Submit report to technical committee for consideration | Consider Report | [14 empty] | 2000
Activity 3: Organise Stakeholders workshop to brainstorm and identify fund raising activities | Organise workshop for stakeholders to consider and select fundraising activities | Organise workshops, suggest activities | [14 empty] | 10000 | 2000
Activity 4: Implement fund raising activities | Implement the activities | Facilitate activities | [14 empty] | 18000 | 3600
Sub-Action 5h: Grant Application:
Activity 1: Hold planning meetings | Hold meetings and consider available grants | Suggest grant winning ideas | [12 empty] | 3 grants applications submitted each year |  | 2000 |  |  | Centre Management
Activity 2: Write and apply for grants | Apply for grants | Facilitate applications | [14 empty] | 8000
Action 6: DLI 6: Timeliness/Quality of Financial Management
Sub-Action 6a: Procurement and Installation of ICT Facilities at the new Postgraduate Centre
Activity 1: Conduct needs assesment | Prepare report on ICT needs at the new Postgraduate centre | [13 empty] | Students and Faculty using ICT facilities for teaching and research |  | 2500 |  |  | Centre Management
Activity 2: Draft report for assessment by Technical Committee | Technical committee to consider report | [15 empty] | 1500
Activity 3: Submit report to Procurement Committee | Report submitted to procurement committee for cinsideration | [15 empty] | 1000
Activity 4: Advertise for tenders | Advertise for tenders | [15 empty] | 5000 | 1000
Activity 5: Contract awarded for purchase and installation(Server and facilities, interactive board and projectors, internet service subscription) | Award of contract | [15 empty] | 55000
Activity 6: Maintenance of installation | Maintenance of facilities installed | [15 empty] | 5000
Sub-Action 6b: Regional Project Review Workshops
Activity 1: Identify and notify participants | Identify and notify regional workshop participants | [13 empty] | Management identifying areas of weakness for improvement |  | 1500 |  |  | Centre Management
Activity 2: Prepare update report on project | Prepare update report on project | [15 empty] | 1000
Activity 3: Submit to CEFTER technical Committee for inputs | Submit report to technical committee for consideration | [15 empty] | 1000
Activity 4: Travels and accomodation cost | Settle workshop expenses | [15 empty] | 26500
Sub-Action 6c: Internal Monitoring and Evaluation Activities
Activity 1: Conduct quaterly review of all CEFTER activities to ensure they meet desired quality and deadlines | Review CEFTER activities quaterly | [15 empty] | 3000 |  |  | M&E team
Action 7: DLI : Institutional Impact
Sub-Action 7a: Development of the Regional Strategy Document
Activity 1: Engage stakeholder consultation process | A committeee of relevant stakeholders will be set up to carry out the process | [13 empty] | A developed and endorsed regional strategy plan |  | 40000 |  |  | University Management
Activity 2: Develop the Regional strategy plan | The regional strategy plan will be developed | [15 empty] | 40000
Activity 3: Present the regional strategy plan to Senate and Council, for approval | The developed regonal strategy plan will be presented to the University Senate and Then Counci for approval | [15 empty] | 10000
Activity 4: Submit the regional strategy approved document to AAU for verification | The regional strategy plan will be presnted for consideration by AAU's independent expert for approval and endorsement | [15 empty] | 10000
Sub-Action 7b: International Institutional Accreditation
Activity 1: Get approval of AAU for a proposed international accrediting body | The AAU must approve accrediting body prior to beginning the acceditation process | [13 empty] | Letter from accrediting body confirming fulfullment of full institutional accreditation |  | 5000 |  |  | Centre Management
Activity 2: Commencement of the process for self study and GAP assessment | Direct engagement with the international accrediting body to undertake either self-study or gap assessment | [15 empty] | 20000
Activity 3: Undergo processes for full international accreditation | The institution will undergo international accreditation with the approved accrediting body following the completion of the self evaluation/gap assesment. | [15 empty] | 25000
Sub-Action 7c: First Round of Institutional benchmarking (PASET)
Activity 1: Complete a data systems-level launch survey on institutional readiness for collecting benchmarking data | [14 empty] | A completed survey indicating progress to the intervention plan and readiness to participate in benchmarking exercise |  | 3000 |  |  | Centre Management
Activity 2: Participate in capacity building training on benchmarking | [16 empty] | 15000
Activity 3: Submission of an institution-level intervention plan | [16 empty] | 4000
Activity 4: Complete a survey to indicate progress | [16 empty] | 3000
Sub-Action 7d: Development and Implementation of FLIP Classroom
Activity 1: Conduct needs assesment | Prepare report on Implementation of FLIP classroom | [13 empty] | Students and Staff making use of FLIP classrooms |  | 1000 |  |  | Centre Management
Activity 2: Draft report for consideration | Consider report and prepare proposal
Activity 3: Submit proposal to Procurement Committee | Submit proposal to communication committee for consideration
Activity 4: Advertise for tenders | Advertise for tenders | [15 empty] | 4000 | 1800
Activity 5: Contract awarded for purchase and installation(Furnishing of lecture recording studio and procurement of recording cameras and electronics) | Award of contract | [15 empty] | 35000
Sub-Action 7e: Expansion of Language Support Unit
Activity 1: Conduct needs assesment | Consider the need for an expansion and draft out modalities | [13 empty] | Language Support facilities being used by CEFTER to conduct bilingual meetings |  | 1000 |  |  | Centre Management
Activity 2: Meet with experts from department of Languages and Linguistics | Meet with experts from Languages and Linguistics department | [15 empty] | 1000
Activity 3: Draft Language support unit guidelines | Draft guidelines for the language support unit | [15 empty] | 2000
Activity 4: Procure more Language translation gadgets | Procure aditional Language translation gadget | [15 empty] | 13000
Activity 5: Train personnel in the use of gadgets | Train personnel on the use of gadgets | [15 empty] | 3000
Action 8: Communication
Activity 1: Develop Communications Strategy | The Communication Strategy should include- objectives, key messages, intended publics, branding and visibility guidelines, communication channels, detailed communication activities and indicators to track implementation of the objectives and the performance of activities outlined. | [13 empty] | One (1) communications strategy each quarter |  | 5000 |  |  | Communications Officer
Activity 2: Regular Website updates | As part of DLI 1, each centre developed a website to further project its activities. Centres should ensure links to their websites are active. Regularly update website with news, originally generated articles, success stories, alumni/student focused articles, stories written from research works etc. (new posts should not only be about calls for applications and upcoming events). These should also be regularly shared with the ACE Impact Communications team at the AAU. Improve website interface (design and navigation) | [13 empty] | Active website links |  | 13000
Activity 3: Regular update of social media platforms | [14 empty] | Minimum of 3 posts weekly |  | 10000
Activity 4: Online repository for research outputs | Communicate the research outputs of studies conducted by the centres and make it easy for stakeholders to access them. | [13 empty] | Visible page/ tab on centre’s website outlining the various research undertaken by the centre. |  | 12000
Activity 5: Media engagement | Engage mainstream media to further disseminate centre’s output/ success stories- sharing compelling articles with local and international media. | [13 empty] | At least 1 mainstream feature quarterly |  | 15000
Activity 6: Production of communication materials- newsletters, brochures, factsheets, infographics, videos, engaging images (photo repository/image bank) | Produce newsletters that highlight success stories, key activities, calls for applications and events of the centre. Produce simple communication materials such as brochures and factsheets. | [13 empty] | Production of quarterly/ bi-annual newsletters |  | 20000
[15 empty] | TOTAL |  | 3234000 | 47900
[16 empty] | Total Estimated Budget ($) | 3234000