## General Work Plan
COUNTRY: NIGERIA
PROJECT NAME: AFRICA CENTRES OF EXCELLENCE FOR DEVELOPMENT IMPACT (ACE IMPACT)
CENTRE NAME: CENTRE FOR FOOD TECHNOLOGY AND RESEARCH WORK PLAN (JANUARY - DECEMBER 2022)
Year 2022
Activity No | ACTIVITY | SUB-ACTIVITY | JUSTIFICATION | ESTIMATED BUDGET ($) | REMARKS | RESPONSIBLE UNIT
[7 empty] | January | February | March | April | May | June | July | August | September | October | November | December
1.1 | Review of Existing Curricular for Relevant PhD Programs | Activity 1: Conduct needs assesment | Students will be admitted into the reviewed PhD programs | 2500 |  | Departments, Faculty, Post graduate School
|  | Activity 2: Draft needs assessment for consideration by Technical Committee |  | 2500
|  | Activity 3: Organise Stakeholders' workshop to review curricula |  | 20000
1.2 | Review of Existing Curricular for Relevant MSC Programs | Activity 1: Conduct needs assesment | Students will be admitted into the reviewed MSc programs | 2500 |  | Departments, Faculty, Post graduate School
|  | Activity 2: Draft needs assessment for consideration by Technical Committee |  | 2500
|  | Activity 3: Organise Stakeholders' workshop to review curricula |  | 20000
1.3 | Training of Farmers/Food Handlers in Safe Hygiene, Transportation of Produce to Markets | Activity 1: Conduct needs assesment | Use of new modules by farmers to improve their income. | 500 |  | Centre Management
|  | Activity 2: Prepare report and submit to Technical committee for consideration |  | 500
|  | Activity 3: Organise Stakeholders' workshop for industries and local fabricators |  | 3000
|  | Activity 4: Identify suitable modules for safe transportation of fruits and vegetables, grains, roots and tubers |  | 500
|  | Activity 5: Identify suitable communities to test run the modules |  | 500
|  | Activity 6: Train community members in the use of developed modules |  | 5000
1.4 | Training of Faculty in Innovative University Teaching | Activity 1: Conduct needs assesment | Students will benefit from new innovative teaching methods. There will also be an increase in number of faculty using innovative teaching methods. | 2000 |  | Centre Management
|  | Activity 2: Draft needs assessment report for consideration by Technical Committee |  | 1000
|  | Activity 3: Organise Trainer of Trainers Workshop involving new partners in innovative teaching and supervision |  | 6000
|  | Activity 4: Mobilise partners for cascade training and mainstreaming innovative teaching methods in institutions and schools |  | 11000
1.5 | Implementation of Short Term Courses(Including Online) | Activity 1: Conduct needs assesment to identify three to four countries in West and Central Africa for training | Graduates from short-term training can be employed or they can establish businesses. | 10000 |  | Centre Management
|  | Activity 2: Develop a suitable curriculum for training. Train resource persons in country and identify trainees |  | 10000
|  | Activity 3: Develop program and implement |  | 20000
1.6 | Training of Technologist and Laboratory Automation | Activity 1: Conduct needs assesment to identify the areas of need | Number of trained laboratory technologist are needed in the departments. | 5000 |  | Centre Management
|  | Activity 2: Conduct survey to identify national and international institutions with best training facilities |  | 2000
|  | Activity 3: Identify and send suitable candidates for training |  | 33000
1.7 | Student Recruitment | Activity 1: Advertise Senate approved programs on CEFTER website | Student need to register and undertake lectures in the Centre to fill the Regional quota | 2500 |  | Centre Management
|  | Activity 2: Advertise Senate approved programs on local and regional print media |  | 12500
|  | Activity 3: Technical committee meets to consider shortlisted candidates for admission |  | 2500
|  | Activity 4: Postgraduate Board meets and approves admission list |  | 2500
1.8 | Training of Students/Staff on use of ICT for learning | Activity 1: Conduct needs assessment | Students and Staff will use advanced software for their learning/teaching and research | 500 |  | Centre Management
|  | Activity 2: Identify the software suitable for enhanced students learning |  | 500
|  | Activity 3: Identify and engage a suitable resource person |  | 1000
|  | Activity 4: Organise training |  | 13000
2.1 | Development of the Regional Strategy Document | Activity 1: Engage stakeholder consultation process |  | 40000 |  | Project Technical Committee
|  | Activity 2: Develop the Regional strategy plan |  | 40000
|  | Activity 3: Present the regional strategy plan to Senate and Council, for approval |  | 10000
|  | Activity 4: Submit the regional strategy approved document to AAU for verification |  | 10000
2.2 | Second West and Central Africa Post Harvest Congress | Activity 1: Hold Planning Meetings | Scientific findings will be presented and there will be an exhibition. | 20000 |  | Centre Management
|  | Activity 2: Stakehoder Drive |  | 20000
|  | Activity 3: Venue |  | 15000
Activity 4: Feeding at the Congress
Activity 5: Conference bags and other materials
Activity 6: Travels(Local and International)
2.3 | CEFTER Thematic Annual Research Grant | Activity 1: Hold planning meetings | Annual grants need to be awarded. | 10000 |  | Centre Management
|  | Activity 2: Receive and review applications |  | 5000
|  | Activity 3: Award grants |  | 35000
2.4 | Funding Peer Reviewed publications from CEFTER Staff and Students | Activity 1: Students and faculty publications submitted to CEFTER publications committee | To enhance the number of publications accepted by Association of African Universities (AAU) Monitoring Committee. |  |  | Centre Management
|  | Activity 2: The committee reviews and shortlists good quality publications |  | 1000
|  | Activity 3: Shortlisted publications sent to experts for peer review |  | 1000
|  | Activity 4: Payment of publication charges |  | 4000
|  | Activity 5: Subscription to Journals |  | 4000
2.5 | Procurement and Installation of ICT Facilities at the new Postgraduate Centre | Activity 1: Conduct needs assesment | ICT faclities will facilitate teaching and learning | 2500 |  | Centre Management
|  | Activity 2: Draft report for assessment by Technical Committee |  | 1500
|  | Activity 3: Submit report to Procurement Committee |  | 1000
|  | Activity 4: Advertise for tenders |  | 5000
|  | Activity 5: Contract awarded for purchase and installation(Server and facilities, interactive board and projectors, internet service subscription) |  | 60000
Activity 6: Maintenance of installation
2.6 | Construction of CEFTER Food Technology Innovation Complex (CEFTIC) | Activity 1: Award contract | Construction of the innovative complex is needed for research and for IGR purposes toward sustainbility. |  |  | Centre Management
|  | Activity 2: Construction of complex |  | 685000
2.7 | Development and Implementation of FLIP Classroom | Activity 1: Conduct needs assesment | Students and staff use of FLIP classrooms | 1000 |  | Centre Management
Activity 2: Draft report for consideration
Activity 3: Submit proposal to Procurement Committee
|  | Activity 4: Advertise for tenders |  | 9000
|  | Activity 5: Contract awarded for purchase and installation(Furnishing of lecture recording studio and procurement of recording cameras and electronics) |  | 35000
3.2 | Participation at Regional Conferences by Staff and Students | Activity 1: Conduct needs assesment | Mainstreaming of improved learning and teaching methods in the institutions. | 2500 |  | Centre Management
|  | Activity 2: Travel and accommodation cost for staff and students at regional Conferences |  | 15000
|  | Activity 3: Prepare report/proceedings and circulate |  | 2500
3.3 | National Conference and Seminar by Staff and Students | Activity 1: Conduct needs assesment | Mainstreaming of improved learning and teaching methods in the institutions. | 1250 |  | Centre Management
|  | Activity 2: Organise national stakeholder workshop |  | 7500
|  | Activity 3: Prepare report/proceedings and circulate |  | 1250
3.4 | Expansion of Language Support Unit | Activity 1: Conduct needs assesment | CEFTER needs Language Support facilities to conduct bilingual meetings | 1000 |  | Centre Management
|  | Activity 2: Meet with experts from department of Languages and Linguistics |  | 1000
|  | Activity 3: Draft Language support unit guidelines |  | 2000
|  | Activity 4: Procure more Language translation gadgets |  | 13000
|  | Activity 5: Train personnel in the use of gadgets |  | 3000
3.5 | Procurement of Small Equipment and Consumables | Activity 1: Conduct needs assesment with departments and partners | Students and staff needs the facilities procured for research and teaching. | 2500 |  | Centre Management
|  | Activity 2: Draft report for consideration |  | 1500
|  | Activity 3: Submit Proposal to procurement committee |  | 1000
|  | Activity 4: Advertise for tenders |  | 5000
|  | Activity 5: Contract awarded for purchase and installation (GCMS for Chemistry lab, FITR Spectrometer, Software and informatics) |  | 60000
3.7 | Student-Faculty Grant (CPSS) | Activity 1: Students and faculty complete and submit application form | Students and Faculty need the grants for conducting research on approved projects. |  |  | Centre Management
|  | Activity 2: The Scholarship and Grants Committee meets and shortlists candidates for interview |  | 2500
|  | Activity 3: Shortlisted candidates defend their proposals before the committee |  | 2500
|  | Activity 4: Disbursement to successful grant applicants |  | 25000
3.8 | Student Support/Scholarships | Activity 1: Conduct needs assesment | Students needs Student Support/ Scholarship. | 5000 |  | Centre Management
Activity 2: Students Complete application forms seeking for support/scholarship
|  | Activity 3: CEFTER Scholarship and Grants Allocation Committee meets to Shortlist qualified students |  | 5000
Activity 4: Shortlisted students forwarded to the Vice Chancellor for Approval
|  | Activity 5: Funding for scholarship awarded to students annually. Covers tuition, accommodation and living expensis |  | 120000
3.9 | Establishment of Regional Research Groups | Activity 1: Conduct needs assesment for establishment of regional working groups | To encourage joint publications in high quality journals. | 4000 |  | Centre Management, Regional Partners, Heads of Departments
|  | Activity 2: Organise a regional faculty stakeholders workshop to formation of regional working groups and how to network |  | 14000
|  | Activity 3: Draft reports and share |  | 2000
4.1 | Partnership Activities | Activity 1: Training of Staff at MSc, PhD levels: Study fellowship | To implement and complete agreed activities for each quarter. | 80000 |  | Project Technical Committee
|  | Activity 2: Student Internships (This includes accomodation, monthly stipend, transport, supervision and consumables) |  | 80000
|  | Activity 3: Joint Projects |  | 50000
|  | Activity 4: Short courses training: Local and international travels |  | 70000
4.2 | Faculty and Students Food Post-harvest Week | Activity 1: Conduct needs assesment | This will lead to Students and entrepreneurs establish business using food products and successful patenting of some food products | 1000 |  | Centre Management
|  | Activity 2: Identify crops and assign to students groups |  | 1000
|  | Activity 3: Assign faculty to student groups as mentor |  | 1000
|  | Activity 4: Student identify food products and prepare budgets |  | 8000
|  | Activity 5: Funding |  | 14000
4.3 | CEFTER Enterprise Development | Activity 1: Hold planning meetings | One start-up per year in a relevant area to encourage entrepreneurs | 10000 |  | Centre Management
|  | Activity 2: Receive and review applications |  | 15000
|  | Activity 3: Setup small and medium scale Funding for three year start-ups per year. 3 winning groups in the enterprise competition will use the fund to set up an agro based small scale enterprise |  | 75000
4.4 | Produce and Circulate flyers, Posters and Monographs | Activity 1: Conduct needs assesment | Targetted at creating awareness and desimination of research findings. | 2000 |  | Centre Management
|  | Activity 2: Prepare report and submit to Technical committee for consideration |  | 1000
|  | Activity 3: Set up an editorial unit and print approved quantity of fliers |  | 12000
4.5 | Provision of Extension and Community Awarness on Post-Harvest Losses | Activity 1: conduct needs assesment | For community members to adopt improved processing and preservation techniques | 1000 |  | Centre Management
|  | Activity 2: Prepare report and submit to Technical Committee for consideration |  | 1000
|  | Activity 3: Prepare a report on level of post-harvest losses accross crop value chain in West and central Africa |  | 3000
|  | Activity 4: Organise yearly community awareness campaigns in selected countries in West and Central Africa |  | 10000
4.6 | Student Intership | Activity 1: Conduct needs assesment | Students deployed to institutions for internship on a yearly basis. | 2000 |  | Centre Management
Activity 2: Identify Industrial and sectoral Partners for students' internship
|  | Activity 3: Develop internship manuals |  | 1000
|  | Activity 4: Develop Schedule for Student distribution |  | 12000
5.1 | Regional Project Review Workshops | Activity 1: Identify and notify participants | Management implementing areas of weakness for improvement. | 1500 |  | Centre Management
|  | Activity 2: Prepare update report on project |  | 1000
|  | Activity 3: Submit to CEFTER technical Committee for inputs |  | 1000
|  | Activity 4: Travels and accomodation cost |  | 26500
5.2 | Setup and maintenance of graduate Tracking System | Activity 1: Hold planning meetings | Tracking of cefter graduates of 2016, 2017, 2018 | 1000 |  | Centre Management
|  | Activity 2: Development and hosting of graduate tracking system online |  | 5000
|  | Activity 3: Salary for 2 staff in the graduate tracking unit |  | 9000
5.3 | Internal Monitoring and Evaluation Activities | Activity 1: Conduct quaterly review of all CEFTER activities to ensure they meet desired quality and deadlines | Internal Monitoring Team ensure timely response to all AAU monitoring requirements. | 3000 |  | Centre Management
5.4 | International Institutional Accreditation | Activity 1: Get approval of AAU for a proposed international accrediting body |  | 5000 |  | Centre Management
|  | Activity 2: Commencement of the process for self study and GAP assessment |  | 20000
|  | Activity 3: Undergo processes for full international accreditation |  | 25000
5.5 | Setup of Phd Offices | Activity 1: Design of PhD offices | To design and furnish offices for PhD candidates | 5000 |  | Centre Management
|  | Activity 2: Furnishing of the offices |  | 45000
5.6 | First Round of Institutional benchmarking (PASET) | Activity 1: Complete a data systems-level launch survey on institutional readiness for collecting benchmarking data |  | 3000 |  | Centre Management
|  | Activity 2: Participate in capacity building training on benchmarking |  | 15000
|  | Activity 3: Submission of an institution-level intervention plan |  | 4000
|  | Activity 4: Complete a survey to indicate progress |  | 3000
6.1 | Fund Raising Activities | Activity 1: Conduct needs assesment | The Project needs Revenue |  |  | Centre Management
|  | Activity 2: Prepare report and submit to Technical Committee |  | 2000
|  | Activity 3: Organise Stakeholders workshop to brainstorm and identify fund raising activities |  | 10000
|  | Activity 4: Implement fund raising activities |  | 18000
6.2 | Grant Application | Activity 1: Hold planning meetings | The project needs funding from other sources | 2000 |  | Centre Management
|  | Activity 2: Write and apply for grants |  | 18000
6.3 | National/Regional Post-harvest Clinic/activities | Activity 1: Conduct needs assesment | The community members need to adopt improved techniques for food preservation and processing. | 4000 |  | Centre Management
|  | Activity 2: Draft report for consideration by Technical Committee |  | 1000
|  | Activity 3: Identify Communities for participatory conduct of Post-Harvest Clinic |  | 5000
|  | Activity 4: Design curriculum and train resource persons from the communities |  | 10000
6.4 | Installation of 50Kva Solar Power to the new CEFTER Complex | Activity 1: Advertise for tenders |  | 25000
|  | Activity 2: Contract awarded for purchase and installation of Solar panels, Batteries, Inverters and smart grid system | To make up for the irregular power supply | 85000
6.5 | Provision of Water supply at the new CEFTER Complex | Activity 1: Conduct needs assesment and Draft report for consideration | Provision of water for staff at the office premises and in the student hostels | 1000
Activity 2: Submit Proposal to procurement committee
Activity 3: Advertise for tenders
|  | Activity 4: Contract awarded |  | 40000
7.1 | Communication | Activity 1: Dissemination of outputs | Publicity | 10000
|  | Activity 2: Media visibility | Publicity | 15000
| Total |  |  | 2314000
| Operating Expenses 10% |  |  | 231400
| Grand Total |  |  | 2545400

## Procurement Plan Works
COUNTRY: NIGERIA
PROJECT: AFRICA CENTRES OF EXCELLENCE FOR DEVELOPMENT IMPACT (ACE IMPACT)
Loan No
NAME OF INSTITUTION: BENUE STATE UNIVERSITY MAKURDI
WORKS | [8 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
|  |  | BASIC DATA | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  |  | Contract Implementation
S/NO. | Description* | Package Number | Lot Number | Estimated Amount in US $ | Procurement Method | Pre-or Post Qualification | Prior or Post Review | Plan vs. Actual | Prep & Submission by Ex Agency | No-objection Date | On-line UNDB Gateway Nat Press | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount in US$ | Date Contract Award | Date Contract Advert | Date Contract Signature | Opening of Let of Credit | Arrival of Goods
| Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | Plan | 4 - 7 wks | 1 - 1.5 wks | 1.5 - 2 wks | 6 to | 12 wks | 1.5 - 3 wks | 1 - 1.5 wks | Plan |  | 1 wk |  | 1.5-3 wks
[6 empty] | add 7-13 wks |  | Actual | [7 empty] | Actual
GOODS
1 | Construction of CEFTER Food Tech Innovation Complex |  |  | 685000 | RFB | Post Qualification | N\A |  | N\A | N\A | N\A | 2022-04-11 | 2022-04-27 | 2021-04-29 | N\A |  | 685000 | 2022-05-02 | N\A | 2022-05-03 | N\A | 16/9/2022
2 | Installation of 50Kva Solar power to the new CEFTER complex |  |  | 110000 | RFB | Post Qualification | N\A |  | N\A | N\A | N\A | 2022-04-11 | 2022-06-01 | 2022-06-30 | N/A |  | 110000 | 2022-07-03 | N/A | 2022-07-04 | N/A | 2022-09-25
3 | Provision of water supply to the new CEFTER complex |  |  | 41000 | RFB | Post Qualification | N\A |  | N\A | N\A | N\A | 2022-01-05 | 2011-01-25 | 2022-01-30 | N/A |  | 41000 | 2022-02-01 | N/A | 2022-02-15 | N/A | 2022-03-31
| Total Cost |  |  | 836000 | [12 empty] | 795000
| Fill gray cells only! |  |  | EXCHANGE RATE: ₦480= U.S. $1.00

## Procurement Plan Goods
COUNTRY: NIGERIA
PROJECT: AFRICA CENTRES OF EXCELLENCE FOR DEVELOPMENT IMPACT (ACE IMPACT)
Loan No
NAME OF INSTITUTION: BENUE STATE UNIVERSITY MAKURDI
GOODS | [8 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
|  |  | BASIC DATA | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  |  | Contract Implementation
S/NO. | Description* | Package Number | Lot Number | Estimated Amount in US $ | Procurement Method | Pre-or Post Qualification | Prior or Post Review | Plan vs. Actual | Prep & Submission by Ex Agency | No-objection Date | On-line UNDB Gateway Nat Press | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount in US$ | Date Contract Award | Date Contract Advert | Date Contract Signature | Opening of Let of Credit | Arrival of Goods | Inspection Final Acceptance
| Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | Plan | 4 - 7 wks | 1 - 1.5 wks | 1.5 - 2 wks | 6 to | 12 wks | 1.5 - 3 wks | 1 - 1.5 wks | Plan |  | 1 wk |  | 1.5-3 wks
[6 empty] | add 7-13 wks |  | Actual | [7 empty] | Actual
GOODS
1 | Procurement and instalation ICT facilities at new PG Centre |  |  | 70000 | RFQ | Post Qualification | Post Review |  |  | NA |  | 2022-01-01 | 2022-01-26 | 2022-01-28 | NA |  | 70000 | 2022-01-31 |  | 2022-02-01 |  | 2022-04-24
2 | Development and Implementation of FLIP Classroom |  |  | 45000 | RFP | Post Qualification | Post Review |  |  | NA |  | 2022-01-13 | 2022-01-28 | 2022-01-31 | NA |  | 45000 | 2022-01-31 |  | 2022-02-01 |  | 2022-04-24
3 | Procurement of small Lab. Equipments and Consumables |  |  | 70000 | RFQ | Post Qualification | Post Review |  |  | NA |  | 2022-01-14 | 2022-01-29 | 2022-01-31 | NA |  | 70000 | 2022-02-01 |  | 2022-02-02 |  | 26/9/2024
4 | Set up of PHD Offices |  |  | 50000 | RFB | Post Qualification | Post Review |  |  | NA |  | 2022-01-18 | 2022-02-04 | 2022-02-06 | NA |  | 50000 | 2022-02-12 |  | 2022-02-14 |  | 2022-11-07
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
| Total Cost |  |  | 235000 | [12 empty] | 235000
| Fill gray cells only! |  |  | EXCHANGE RATE: ₦480= U.S. $1.00

## Procurement Plan Consultancy
COUNTRY: NIGERIA
PROJECT: AFRICA CENTRES OF EXCELLENCE FOR DEVELOPMENT IMPACT (ACE IMPACT)
CREDIT NO:
NAME OF INSTITUTION: BENUE STATE UNIVERSITY MAKURDI
For Contracts under projects approved before the May 2002 Guidelines
|  |  | If Post-Review, No-objection Dates are not needed | [5 empty] | Request for EOI (where required)
CONSULTANCY |  |  | Contract Type |  |  |  | Preparation Request for Proposals |  |  |  | Short List |  |  | Consultant Proposals |  | Proposal Evaluation and Negotiation for Projects after May 2002 Technical (T) & Financial (F) and Negotions (N) | [5 empty] | Draft Contract |  | Contract Finalization |  |  |  |  | Contract Implementation
S/No. | Description* | Selection Method | Lumpsum or Time-Based | Estimated Amount in US$ '000 | Prior/Post Review | Plan vs. Actual | Prep & Submission by Ex Ag | No-objection Date | On-line UNDB Gateway Nat Press | Lead-time before shortlist | Submission Date | No-objection Date | Plan vs. Actual | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | No-objection Evaluation Report (T) | Opening Financial Proposals | Preparation Eval Report (T) (F) | Negotiations (N) | Plan vs. Actual | Submission Date | No-objection Date | Contract Amount in US$ '000 | Contract Award | Date Contract Advert | Contract Signature | Plan vs. Actual | Mobilization Advance Payment | Draft Report | Final Report | Final Cost US$ '000
| Norm Duration of Proc Steps |  |  |  |  | Plan | 3 - 6 wks | 1 - 2 wks | 1 - 1.5 wks | 2 wks |  | 1 - 2 wks | Plan | 4 to | 12 wks | 2 - 3 wks | 0.5 - 2 wks | 2 wks | 1 - 2 wks | 2 wks | Plan | 1 - 2 wks | 1 - 2 wks |  | 1 wk |  | 1 - 3 wks | Plan
[6 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
List of Contracts
1 | Setup and maintenance of graduate tracking system | DIR |  | 15000 |  | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
|  | DIR | TIME BASE |  |  | Actual | [6 empty] | Actual | 2022-01-15 | 03/02/2022 | 06/02/2022 | NA | NA |  |  | Actual |  |  | 15000 | 09/02/2022 |  | 12/02/2022 | Actual |  |  |  | 15000
2 | Development of Regional Strategy Document | CD |  | 100000 | Prior R | Plan |  | NA | NA | NA |  |  | Plan | [7 empty] | Plan | [6 empty] | Plan
|  | CD | TIME BASE |  |  | Actual | [6 empty] | Actual | 2022-01-05 | 2022-01-15 | 2022-01-31 |  |  |  |  | Actual | NA | NA | 100000 | 2022-02-15 | NA | 28/02/2022 | Actual |  |  |  | 100000
3 | International Institution Accreditation | PPP |  | 50000 |  | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
|  | PPP | TIME BASE |  | Prior R | Actual |  | NA | NA | NA |  |  | Actual | 2022-01-05 | 2022-03-06 | 2022-06-06 |  |  |  |  | Actual | NA | NA | 50000 | 2022-06-30 | NA | 2022-07-01 | Actual |  |  |  | 50000
4 | First Round of Institutional Benchmarking (PASET)s | DIR |  | 25000 |  | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
|  | DIR | TIME BASE |  | Prior R | Actual |  | NA | NA | NA |  |  | Actual | 2022-01-13 | 2022-01-20 | 2022-03-01 |  |  |  |  | Actual | NA | NA | 25000 | 2022-04-06 | NA | 2022-05-05 | Actual |  |  |  | 25000
5 | Communication | PPP |  | 25000 |  | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
|  | PPP | TIME BASE |  | Prior R | Actual |  | NA | NA | NA |  |  | Actual | [7 empty] | Actual | NA | NA |  |  | NA |  | Actual
25000
| TOTAL AMOUNT |  |  | 215000 |  | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[6 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual

## Procurement Plan Training
COUNTRY: NIGERIA
PROJECT: AFRICA CENTRES OF EXCELLENCE FOR DEVELOPMENT IMPACT (ACE IMPACT)
CREDIT NO: IDA
NAME OF INSTITUTION: BENUE STATE UNIVERSITY MAKURDI
TRAINING/CAPACITY BUILDING
S/N | DESCRIPTION | NAMES OF PARTICIPANTS | OBJECTIVES | OUTCOME | TRAINING LOCATION | COST
1 | Development and training of farmers/food handlers in safe hygienic transportation of produce to markets | farmers/food handlers/resource persons | use of new modules by formers to improve their income | sustainable use of safe and hygienic transportation modules for produce to markets |  | 10000
2 | Training of Faculty in Innovative University Teaching | Accademic staff | Students benefitting from new innovative teaching methods. Increase in number of faculty using innovative teaching methods | Curricula for innovative University teaching developed |  | 20000
3 | Training of Technologists and laboratory automation | staff | Generation of high quality technologist and laboratory automation personnel | Qualified candidates identified |  | 40000
4 | Training of Student/Staff on use of ICT for learning | staff/students | Students and staff using advanced software for their learning/teaching and research | Students and staff equipped for active learning |  | 15000
[5 empty] | TOTAL | 85000

## Disbursement Plan
COUNTRY: NIGERIA
PROJECT: AFRICA CENTRES OF EXCELLENCE FOR DEVELOPMENT IMPACT (ACE IMPACT)
CENTRE: CENTRE FOR FOOD TECHNOLOGY AND RESEARCH
CREDIT NO: IDA
DISBURSEMENT PLAN (JANURY - DECEMBER, 2022)
S/N | ACTIVITIES | OBJECTIVE | AMOUNT | MONTHS
|  |  | $ | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | TOTAL
GOODS
1 |  | Procurement and instalation ICT facilities at new PG Centre | AMOUNT $: 70000; MONTHS JAN: 70000; MONTHS TOTAL: 70000
2 |  | Development and Implementation of FLIP Classroom | AMOUNT $: 45000; MONTHS JAN: 45000; MONTHS TOTAL: 45000
3 |  | Procurement of small Lab. Equipments and Consumables | AMOUNT $: 70000; MONTHS FEB: 70000; MONTHS TOTAL: 70000
4 |  | Set up of PHD Offices | AMOUNT $: 50000; MONTHS FEB: 50000; MONTHS TOTAL: 50000
5 |  |  | MONTHS TOTAL: 0
TRAINING
1 |  | Development and training of farmers/food handlers in safe hygienic transportation of produce to markets | AMOUNT $: 10000; MONTHS APR: 10000; MONTHS TOTAL: 10000
2 |  | Training of Faculty in Innovative University Teaching | AMOUNT $: 20000; MONTHS MAR: 20000; MONTHS TOTAL: 20000
3 |  | Training of Technologists and laboratory automation | AMOUNT $: 40000; MONTHS MAY: 40000; MONTHS TOTAL: 40000
4 |  | Training of Student/Staff on use of ICT for learning | AMOUNT $: 15000; MONTHS SEP: 15000; MONTHS TOTAL: 15000
CONSULTANCIES
1 |  | Setup and maintenance of graduate tracking system | AMOUNT $: 15000; MONTHS FEB: 15000; MONTHS TOTAL: 15000
2 |  | Development of the Regional Strategy Document | AMOUNT $: 100000; MONTHS JAN: 100000; MONTHS TOTAL: 100000
3 |  | International Institutional Accreditation | AMOUNT $: 50000; MONTHS MAR: 50000; MONTHS TOTAL: 50000
4 |  | First Round of Institutional Benchmarking (PASET) | AMOUNT $: 25000; MONTHS JUN: 25000; MONTHS TOTAL: 25000
5 |  | Communication | AMOUNT $: 25000; MONTHS JAN: 25000; MONTHS TOTAL: 25000
6
OPERATING COST
1 |  | Review of existing curricula for relevant Ph.D. programs in Biological Science, Chemistry, Vocational and Technical Education, Physics, Economics, Sociology | AMOUNT $: 25000; MONTHS JAN: 25000; MONTHS TOTAL: 25000
2 |  | Review of existing curricula for relevant M.Sc. programs in Biological Science, Chemistry, Vocational and Technical Education, Physics, Economics, Sociology | AMOUNT $: 25000; MONTHS MAY: 25000; MONTHS TOTAL: 25000
3 |  | Implementation of short term courses (including online) | AMOUNT $: 40000; MONTHS FEB: 40000; MONTHS TOTAL: 40000
4 |  | Student recruitment | AMOUNT $: 20000; MONTHS JUN: 20000; MONTHS TOTAL: 20000
6 |  | Second west and central Africa Post Harvest Congress | AMOUNT $: 55000; MONTHS DEC: 55000; MONTHS TOTAL: 55000
7 |  | CEFTER Thematic Annual Research Grant | AMOUNT $: 50000; MONTHS MAR: 50000; MONTHS TOTAL: 50000
8 |  | Funding for peer reviewed Publication | AMOUNT $: 10000; MONTHS JAN: 10000; MONTHS TOTAL: 10000
9 |  | Participation at regional conferences by staff and students | AMOUNT $: 20000; MONTHS JAN: 20000; MONTHS TOTAL: 20000
10 |  | National Conference and Seminar by Staff and Students | AMOUNT $: 10000; MONTHS JAN: 10000; MONTHS TOTAL: 10000
11 |  | Expansion of language support Unit | AMOUNT $: 20000; MONTHS SEP: 20000; MONTHS TOTAL: 20000
12 |  | Student-Faculty Grant (CPSS) | AMOUNT $: 30000; MONTHS OCT: 30000; MONTHS TOTAL: 30000
13 |  | Student Support/Scholarships | AMOUNT $: 130000; MONTHS JUL: 130000; MONTHS TOTAL: 130000
14 |  | Establishment of regional research groups | AMOUNT $: 20000; MONTHS AUG: 20000; MONTHS TOTAL: 20000
15 |  | Partnership activities | AMOUNT $: 280000; MONTHS OCT: 280000; MONTHS TOTAL: 280000
16 |  | Faculty and Student food/postharvest week activities. | AMOUNT $: 25000; MONTHS NOV: 25000; MONTHS TOTAL: 25000
17 |  | Enterprise Development | AMOUNT $: 100000; MONTHS MAY: 100000; MONTHS TOTAL: 100000
18 |  | Produce and Circulate Monographs and Newsletter targeted at awareness creation | AMOUNT $: 15000; MONTHS OCT: 15000; MONTHS TOTAL: 15000
19 |  | Provision of extension services | AMOUNT $: 15000; MONTHS JAN: 15000; MONTHS TOTAL: 15000
20 |  | Student Internship | AMOUNT $: 15000; MONTHS DEC: 15000; MONTHS TOTAL: 15000
21 |  | Regional project review workshops | AMOUNT $: 30000; MONTHS MAR: 30000; MONTHS TOTAL: 30000
22 |  | Monitoring and evaluation | AMOUNT $: 3000; MONTHS APR: 3000; MONTHS TOTAL: 3000
23 |  | Institutional Reforms for Regional Strategy, Institutional Accreditation, Participation in PASSET and Promotion of Institutional Impact | AMOUNT $: 35000; MONTHS FEB: 35000; MONTHS TOTAL: 35000
24 |  | Establishment of Sectoral advisory Board | AMOUNT $: 10000; MONTHS DEC: 10000; MONTHS TOTAL: 10000
25 |  | Fund raising Activities | AMOUNT $: 30000; MONTHS JAN: 30000; MONTHS TOTAL: 30000
26 |  | Grants Application | AMOUNT $: 20000; MONTHS JAN: 20000; MONTHS TOTAL: 20000
27 |  | National/Regional Postharvest clinic/activities | AMOUNT $: 20000; MONTHS SEP: 20000; MONTHS TOTAL: 20000
28 |  | Contingency | AMOUNT $: 30000; MONTHS JAN: 30000; MONTHS TOTAL: 30000
0
| TOTAL |  | 1618000 | 400000 | 210000 | 150000 | 13000 | 165000 | 45000 | 130000 | 20000 | 55000 | 325000 | 25000 | 80000 | 1618000