## Work Plan
AFRICA CENTRES OF EXCELLENCE (ACE): CENTRE FOR FOOD TECHNOLOGY AND RESEARCH
BENUE STATE UNIVERSITY MAKURDI WORK PLAN (JANUARY - DECEMBER 2017)
| CMP XX | [7 empty] | Year 2017
Activity No | COMPONENT | SUB-COMPONENT | ACTIVITIES | OBJECTIVE | JUSTIFICATION | OUTPUT | ESTIMATED BUDGET ($) | RESPONSIBLE UNIT | January - December 2017
[9 empty] | January | Febrary | March | April | May | June | July | August | September | October | November | December
Component 1: Strengthening Africa Centers of Excellence
1 |  |  | Rehabilitating Existing Facilities: Laboratories and refurblishing of additional Lecture rooms | To refurbish old relevant laboratories to standard | It is important to improve on the existing facilities to meet up with emerging research needs | Old Laboratories refurbished and in use | 55150 | Centre management
2 |  |  | Construction of CEFTER PG centre | To Build a new complex containing lecture rooms and food Science Labs | The University provided a temporary complex which needs to be vacated in three years | Permanent CEFTER complex completed and in use | 800025 | Centre management
3 |  |  | Establishing of language support unit | To set up a language lab to support students from Francophone countries | The need to support students from any part of the region | A functional Language Support Unit | 19000 | Project Technical Comitee
4 |  |  |  | Safeguards | Safeguard | Audits reports ready | 17500 | Bursary
5 |  |  | Employment and training technicians and qualified support staff (Training of staff on new equiptment and recruitment process fees) | To recruit where necessary and train Technologist in relevant areas | Staff need training to man new research equipment | Number of Staff trained | 30000 | Project Technical Comitee
6 |  |  | Student recruitment (Advertisements, portal, travels, interview and printing) | To improve on student numbers through adverts and other means | The need to get students especially those outside Nigeria | Increase in number of students especially non-nationals | 13500 | Centre management
7 |  |  | Scaling up PhD Programmes (increasing students numbers,visiting professors and researchers) Honoraria of non employed staff) | To carter for academeic needs of PhDs and Researchers | PhD research requires a lot more than teaching. | Increase in PhD numbers, visits of international experts and number of conferences attended | 36000 | Centre management
8 |  |  | International Research Collabration and Joint Research Programme among students and Staff | To provide funding for regional and international research activities | Need to Improve quality of research and mobility among staff and students | Number of joint research activities and publications | 60000 | Centre management
9 |  |  | Local travels | To cover cost of travel for project activities within the country | The project requires meetings and other relevant project activities that need to done | All required project activities carried out | 24000 | Centre management
10 |  |  | Faculty Developments :capacity building in curricala and non curricula based programmes | To train staff in relevant teaching and research support | training on modern teaching and research techniques very important | Number of staff trained on short courses | 50000 | Centre management
11 |  |  | Research grant pools (to small and medium scale applied research) | To provide funding for staff and student research | PG education is important and must be acconpanied by research | Number of joint student-staff research | 75000 | Centre management
12 |  |  | Publication in high impact factor journals by faculty and students (cost of publication) | Funding will be available for any article within the ACE | Publications ar required to meet the DLI and excellence at ACE | Increased Number of publications | 15000 | Centre management
13 |  |  | Provide equitable distribution of excellence through affiliation to other institutions (Travels and mettings) | Funding for partnership activities | Collaboration with other institutions very important | Increase in partnership activities | 10500 | Centre management
14 |  |  | Provide broad-based scientific capacity of students through intenships, short courses and SIWES | Funding for travel and student internship activities | To train employable graduates with hands-on training | Completed intership positions | 40000 | Centre management
15 |  |  | Provision of extension and community mobilization services/awareness | Funding for outreach activities to a dedicated project | Outreach activities are an important aspect of the project | Completed outreach activity | 15000 | Centre management
16 |  |  | Ensure social relevance through annual regional stakeholders meeting in participating countries | Funding for attendance of ACE meetings | very relevant and a requirement | Attendance at metings | 35000 | Centre management
17 |  |  | Engagement in joint research project among participating institutions | Funding for joint research activities among partnership institutions in Nigeria | To encourage research on focused topics | Increased Number of joint activities | 20000 | Centre management
18 |  |  | Introdution of regional working groups for research groups | Funding for attendance of ACE meetings and workshops | Needed for regional integration of the project | Successful group meetings | 16000 | Centre management
19 |  |  | Short term exchange programmes within Nigeria | Funding for staff internship at institutions within Nigeria | A conponent of the project and needed for capacity building | Number of short term visits | 15000 | Centre management
20 |  |  | Student Support Scheme for Cefter Students | Funding to provide support for indigent studentswho excell | Very good way of boosting student numbers and ensuring comfort. | Improved student numbers and satisfaction | 150000 | Centre management
21 |  |  | Introdution of short term (professional) courses (design special Agro Bussiness start-up courses for loan takers) | Funding for development of modules for agro value chain players | A good step for developing another outreach program | Developed curricula translated into French and local Languages | 15000 | Centre management
22 |  |  | Research grant pools to support faculty and student's international applied research on post-harvest losses | Funding to support student based small scare research with international collaboration | Very important to internationalise quality of research | Number ans success of joint projects | 25000 | Centre management
23 |  |  | Stakeholder meeting within Nigeria | Funding to cover cost of Stakeholders meeting at NRCRI | Yearly Stakeholders meeting to review project activities | Completed Meeting | 25000 | Centre management
24 |  |  | Develop joint curricula among partnership institution and CEFTER Departments | Funding to cover cost of upgrading curricula at partner institutions | To promote multidiciplinary approach in training students to control post Harvest Losses | New Joint Curriculum | 15000 | Centre management
25 |  |  | Identification of joint training needs for academic and professional staff in post-harvest science and management | Funding to cover cost of Needs assessment | To acertain the training needs for proper planning and implementation | Needs Assessment report | 12000 | Centre management
26 |  |  | Mount short courses,workshops and conferences on topics in post-harvest sciences and management (Food Safety and Hygiene) | Funding to cover of training of 200 food handlers | The course is an annual outreach programe | number of food handlers trained | 15000 | Centre management
27 |  |  | Institute lecture series: First Lecture Series on Impact of Climate change on PHL | Funding to cover cost of Needs assessment | Relevant topical issue in control of PHL | To host one Lecture Series | 20000 | Centre management
28 |  |  | Produce and circulate monographs targeted at awareness creation and extension to rural farmers | Funding to cover cost of developing and printing monograph | Important in Extention services | Monographs produced and circulated | 6000 | Centre management
29 |  |  | Plan for achieving collaborations with International partners Joint research and Accredition activities (partnership Funding/activities with LJMU) | Funding to support joint partner international activities | Activities to build capacity to pursue international accreditation | Number of capacity building programs | 27000 | Centre management
30 |  |  | Start faculty exchanges between CEFTER, and institutions in Africa | Funding to cover cost of travel and relevant activities relating to staff exchange. | regional fellowships an important aspect of the project | Number of regional fellowships | 24000 | Centre management
31 |  |  | Produce revised student handbooks for students | Funding to cover cost of preparimg and printing student manuals | Needed for student information and advertisement | Printed and distributed student manuals | 6000 | Centre management
32 |  |  | Monitoring and evaluation (Travels, stationaries) | Funding to cover cost of travel and and training of team members | Required to assess project implementation | M&E activities | 18000 | Centre management
33 |  |  | Fund raising activities (Meetings, travels, media) | Funding to cover cost of meetings, travel media and other related activities. | Required for sustainability | Meetings and other activities relating to fund raising | 10500 | Centre management
34 |  |  | NgREN Communication Services | Funding to cover cost of subscription and infrastructure | The subscription is needed to upgrade internet access | NgREN subscribed | 300000 | Centre management
35 |  |  | Support services and utilities.(It includes hiring and paying utility staff and other support staff/services) | Funding to cover cost of support staff. It also includes hiring and paying utility staff | To acquire services needed and to keep up with the cleanliness of the environment | Completed service jobs. Tidy and clean environment | 90000 | Centre management
36 |  |  | Upgrade Automated accounting System | Funding to cover cost of upgrading the SAGE accounting system | Needed for efficient accounting | Upgraded version of the Accounting sofware installed and working | 20000 | Centre management
37 |  |  | Upgrading established effective quality assurance and quality improvement policy | Funding to cover cost of developing and producing quality assuarance policy | A requirement in safeguards | Developed policy | 5000 | Centre management
38 |  |  | Provide a strong data management policy for CEFTER (Cosultancy charge) and implementationy | Funding to cover cost of developing and producing data management policy | Needed for incorporate new and modern data | Policy and ready and circulated | 4500 | Centre management
39 |  |  | consultancy services for the construction of PG faculty for cefter complex | Funding to cover cost design and consultancy for building | New construction requirement | Tender document and construction contract | 45037.5 | Centre management
40 |  |  | Purchase of research equipment | funding to cover cost of small scale research equipment | Needed to upgrade labs | procurement of equipment | 150000 | Centre management
41 |  |  | Environmental And Social Management Plan | Funding to cover cost of ESMP | Requirement for new construction | ESMP report ready | 30000 | Centre management
42 |  |  | Use of ICT in delivering Research Excellence :provision of CEFTER PG interactive classroom | Cost of maintenance and upgrade with software subscription | required to keep interactive board system running | ICT facility in place and functional | 26507.14 | Centre management
|  |  | Purchase of stationary and staff computers | Funding to cost of stationaries and potable laptops | Neededfor efficient management | Stationaries and computers procured | 40000
2426219.64

## MINOR WORKS
REVISED SIMPLIFIED PROCUREMENT PLAN FOR ACE PROJECT 2014/2015
1. | General THE EXCHANGED RATE USED IS ₦200 PER US DOLLAR
| Country/Organisation: | BENUE STATE UNIVERSITY,NIGERIA
| Project/Programme: | Center of Excellence in the control of post harvest losses(center for food technology and research)
Loan No:
| Implementing Agency, Address: | BENUE STATE UNIVERSITY,MAKURDI,NIGERIA
World Bank's Approval Date of Procurement Plan:
Date of General Procurement Notice:
| Period Covered by these Procurement Plans: | January, 2017– December, 2017
MINOR WORKS
2. | Prior Review Threshold:
| Procurement Method | Threshold for use of Method (US$) | Prior review Threshold (US$) | Comments
| 1. ICB and LIB (Goods) | N/A | N/A
| 2. NCB (Goods) | N/A | N/A
| 1. ICB (Works) | N/A | N/A
| 4. NCB (Works) | N/A | N/A
| 5. ICB (Non-Consultant Services) | N/A | N/A
| 6. Shopping | N/A | N/A
| 7. Direct Contracting | N/A | N/A
Works
|  | PACKAGE NUMBER | BASIC DATA | [5 empty] | DRAFT BID DOCUMENTS, INCLUDING SPECS AND BOQ, DRAFT SPN |  | IF POST-REVIEW, NO-OBJECTION DATES ARE NOT REQUIRED |  |  | BID EVALUATION |  | CONTRACT FINALIZATION |  |  |  | CONTRACT IMPLEMENTATION
3. | Procurement Packages with Methods and Time Schedule | [9 empty] | SPECIFIC PROCUREMENT NOTICE ADVERT | BIDDING PERIOD
| Description of Contract |  | LOT NUMBR | FIXED PRICE OR BILL OF QUANTITIES | PROCUREMENT METHOD | ESTIMATED AMOUNT (US$) | PRE- OR POST-QUALIFICATION | PRIOR OR POST REVIEW | PREPARATION & SUBMISSION BY EX. AGENCY | NO-OBJECTION DATE | ONLINE UNDB, CLIENT CONNECTION GATEWAY, NAT PRESS | BID INVITATION DATE | BID CLOSING/OPENING | SUBMISSION OF BID EVALUATION REPORT | NO-OBJECTION DATE | CONTRACT AMOUNT (US$) | DATE OF CONTRACT AWARD | DATE OF CONTRACT ADVERT | DATE OF CONTRACT SIGNATURE | MOBILIZATION ADVANCE PAYMENT | SUBSTANTIAL COMPLETION | FINAL ACCEPTANCE | FINAL COST
[7 empty] | 7-13 WKS |  | 4-7 WKS | 1-1.5 WKS | 1.5-2 WKS | 1.5-2 WKS | 6 WKS TO | 12 WKS | 1.5-3 WKS |  | 1 WK |  | 1.5-3 WKS
| Rehabilitating Existing Facilities : ( Laboratories and refurblishing of additional | Plan | 5 | N/A | NCB | 55150 | Post Qualification | Post Review | N/A | N/A | 9th-Feb-17 | 9th-Feb-17 | 20th-Feb-17 | N/A | N/A | 55150 | 2017-03-23 | 2017-03-23 | 7th-Apr-17 | 21st-Apr-17 | 10th-Aug-17 | 29th-sep-17 | ACTUAL COST
Actual
| construction of PG faculty for CEFTER | Plan | 6 | N/A | NCB | 800250 | Post Qualification | Post Review | N/A | N/A | 9th-Feb-17 | 9th-Feb-17 | 20th-Feb-17 | N/A | N/A | 300250 | 2017-03-23 | 2017-03-23 | 7th-Apr-17 | 21st-Apr-17 | 24th-mar-18 | 20th-dec-18 | ACTUAL COST
Actual
| Establishing language support unit | Plan | 7 | N/A | NCB | 19900 | Post Qualification | Post Review | N/A | N/A |  | 9th-Feb-17 | 20th-Feb-17 | N/A | N/A | 19900 | 2017-03-23 | 2017-03-23 | 7th-Apr-17 | 21st-Apr-17 | 10th-Aug-17 | 29th-sep-17 | ACTUAL COST
Actual
| Total Cost |  |  |  |  | 875300

## GOODS
REVISED SIMPLIFIED PROCUREMENT PLAN FOR ACE PROJECT 2017
1. | General THE EXCHANGED RATE USED IS ₦200 PER US DOLLAR
| Country/Organisation: | BENUE STATE UNIVERSITY,MAKURDI,NIGERIA
| Project/Programme: | Center of Excellence in the control of post harvest losses(center for food technology and research)
Loan No:
| Implementing Agency, Address: | BENUE STATE UNIVERSITY,MAKURDI,NIGERIA
World Bank's Approval Date of Procurement Plan:
Date of General Procurement Notice:
| Period Covered by these Procurement Plans: | January, 2017– December, 2017
G O O D S
2. | Prior Review Threshold:
Goods and Non-Consulting (see Note 1)
|  | Threshold | Prior review
| Procurement Method | for use of Method | Threshold | Comments
|  | (US$) | (US$)
| 1. ICB and LIB (Goods) | N/A | N/A
| 2. NCB (Goods) | N/A | N/A
| 1. ICB (Works) | N/A | N/A
| 4. NCB (Works) | N/A | N/A
| 5. ICB (Non-Consultant Services) | N/A | N/A
| 6. Shopping | N/A | N/A
| 7. Direct Contracting | N/A | N/A
|  | PACKAGE NUMBER | BASIC DATA | [5 empty] | DRAFT BID DOCUMENTS, INCLUDING SPECS AND BOQ, DRAFT SPN |  | IF POST-REVIEW, NO-OBJECTION DATES ARE NOT REQUIRED |  |  | BID EVALUATION |  | CONTRACT FINALIZATION |  |  |  | CONTRACT IMPLEMENTATION |  |  |  | LINK TO RESULTS
3. | Procurement Packages with Methods and Time Schedule | [9 empty] | SPECIFIC PROCUREMENT NOTICE ADVERT | BIDDING PERIOD
| Description of Contract |  | LOT NUMBR | FIXED PRICE OR PRICE ADJUSTMENT | PROCUREMENT METHOD | ESTIMATED AMOUNT (US$) | PRE- OR POST-QUALIFICATION | PRIOR OR POST REVIEW | PREPARATION & SUBMISSION BY EX. AGENCY | NO-OBJECTION DATE | ONLINE UNDB, CLIENT CONNECTIONGATEWAY, NAT PRESS | BID INVITATION DATE | BID CLOSING/OPENING | SUBMISSION OF BID EVALUATION REPORT | NO-OBJECTION DATE | CONTRACT AMOUNT (US$) | DATE OF CONTRACT AWARD | DATE OF CONTRACT ADVERT | DATE OF CONTRACT SIGNATURE | MOBILIZATION ADVANCE PAYMENT | SUBSTANTIAL COMPLETION | FINAL ACCEPTANCE | FINAL COST
[7 empty] | 7-13 WKS |  | 4-7 WKS | 1-1.5 WKS | 1.5-2 WKS | 6 TO | 12 WKS | 1.5-3 WKS | 1-1.5 WKS |  | 1 WK |  | 1.5-3 WKS
| LOT 1 RESEARCH/LABORATORY EQUIPMENT | Actual
| Purchase of Research Equipment | Plan | 1 | N/A | NCB | 150571.43 | Post -Qualification | Post Review | N/A | N/A | 17th-feb-17 | 17th-feb-17 | 31st-Mar-17 | N/A | N/A | 150571.43 | 28th-Apr-17 | N/A | 28th-Apr-17 | 15th-May-17 | 12th-Jun-17 | 3rd-oct-17 | ACTUAL COST
Actual
| LOT 2 LABORATORY EQUIPMENT | Plan | 2
| LOT 3 STATIONARY/ STAFF COMPUTERS | Actual
| Purchase of stationary and staff computers | Plan | 3 | N/A | Shoping | 40000 | Post -Qualification | Post Review | N/A | N/A | 2017-03-10 | 16th-Mar-17 | 9th-Apr-17 | N/A | N/A | 40000 | 25th-May-17 | N/A | 30th-May-17 | 5th-Jun-17 | 12th-Jun-17 | 10th-Dec-17 | ACTUAL COST
Actual
| LOT 4 FURNISHING OF CLASSROOMS |  | 4
| Use of ICT in delivering Research Excellence :provision of CEFTER PG interactive classroom | Plan |  | N/A | Shoping | 26507.14 | Post -Qualification | Post Review | N/A | N/A | 17th-Apr-17 | 27th-Apr-17 | 31st-May-17 | N/A | N/A | 26507.14 | 2nd-Jun-17 | N/A | 10th-Jun-17 | 15th-Jun-17 | 12th-Jul-17 | 3rd-oct-17 | ACTUAL COST
Actual
| TOTAL |  |  |  |  | 217078.57
NOTE:
1. In LOT3 and LOT, we apply the shopping procurement procurement method since these items are off-shelf items andwould be carried out more than once as needed.

## OPERATING COST
REVISED SIMPLIFIED PROCUREMENT PLAN FOR ACE PROJECT 2017
1. | General THE EXCHANGED RATE USED IS ₦200 PER US DOLLAR
| Country/Organisation: | BENUE STATE UNIVERSITY NIGERIA
| Project/Programme: | Center of Excellence in the control of post harvest losses(center for food technology and research)
Loan No:
| Implementing Agency, Address: | BENUE STATE UNIVERSITY,MAKURDI,NIGERIA
World Bank's Approval Date of Procurement Plan:
Date of General Procurement Notice:
| Period Covered by these Procurement Plans: | January, 2017–December, 2017
OPERATING COST
2. | Prior Review Threshold:
|  | Threshold | Prior review
| Procurement Method | for use of Method | Threshold | Comments
|  | (US$) | (US$)
| 1. ICB and LIB (Goods) | N/A | N/A | N/A
| 2. NCB (Goods) | N/A | N/A | N/A
| 1. ICB (Works) | N/A | N/A | N/A
| 4. NCB (Works) | N/A | N/A | N/A
| 5. ICB (Non-Consultant Services) | N/A | N/A | N/A
| 6. Shopping | N/A | N/A | N/A
| 7. Direct Contracting | N/A | N/A | N/A
3. | Procurement Packages with Methods and Time Schedule |  | BASIC DATA | [6 empty] | DISBURSEMENT LINKED INDICATORS
| Description of Expenses | Source of Funds | Estimated Amount (US$) | 1st quarter | 2nd quarter | 3rd quarter | 4th quarter | Total Amount (US$) | Plan Vs Actual | DLI/DLR
| Audit expenses (Procurement and Account audit) | WB | 17500 | 3000 | 4000 | 3000 | 7500 | 17500 | Plan
Actual
| Employment and training technicians and qualified support staff (Training of staff on new equiptment and recruitment process fees) | WB | 30000 | 6000 | 7500 | 10500 | 6000 | 30000 | Plan
Actual
| Student recruitment (Advertisements, portal, travels, interview and printing) | WB | 13500 | 3000 |  | 7000 | 3500 | 13500 | Plan
Actual
| Scaling up PhD Programmes (increasing students numbers,visiting and professors and researchers) Honoraria of non employed staff) | WB | 36000 | 6000 | 9000 | 13500 | 7500 | 36000 | Plan
Actual
| International Research Collabration and Joint Research Programme among students faculties | WB | 60000 | 11000 | 15000 | 22500 | 11500 | 60000 | Plan
Actual
| Local Travels | WB | 24000 | 5000 | 6000 | 9000 | 4000 | 24000 | Plan
Actual
| Faculty Developments :capacity building in curricala and non based programmes | WB | 50000 | 9000 | 12500 | 19000 | 9500 | 50000 | Plan
Actual
| Research grant pools (to small and medium scale applied research) | WB | 225000 | 5000 | 5000 | 8500 | 4500 | 225000 | Plan
Actual
| Publication in high impact factor journals by faculty and students (cost of publication) | WB | 15000 | 3000 | 3500 | 5500 | 3000 | 15000 | Plan
Actual
| Provide equitable distribution of excellence through affiliation to other institutions (Travels and mettings) | WB | 10500 | 2000 | 2500 | 4000 | 2000 | 10500 | Plan
Actual
| Provide equitable distribution of excellent high quality open and distant learning | WB | 35000 | 6000 | 8750 | 13500 | 6750 | 35000 | Plan
Actual
| Provide equitable distrbution of excellence and high quality research by instituting doctoral research | WB | 20000 | 4000 | 5000 | 7500 | 3500 | 20000 | Plan
Actual
| provide broad-based scientific capacity of students through intenships, short courses and SIWES | WB | 40000 | 7000 | 10000 | 15000 | 8000 | 40000 | Plan
Actual
| Provision of extension and community mobilization services/awareness | WB | 15000 | 3000 | 3500 | 5500 | 3000 | 15000 | Plan
Actual
| Ensure social relevance through annual regional stakeholders meeting in participating countries NRCRI | WB | 15000 | 3000 | 3500 | 6000 | 2500 | 15000 | Plan
Actual
| Engagement in joint research project among participating institutions | WB | 16000 | 3000 | 4000 | 6000 | 3000 | 16000 | Plan
Actual
| Introdution of regional working groups for research groups | WB | 16000 | 3000 | 6000 | 4000 | 3000 | 16000 | Plan
Actual
| Short term exchange programmes within Nigeria | WB | 15000 | 3000 | 4000 | 5500 | 2500 | 15000 | Plan
Actual
| Schorlaships research and other support services for Cefter Students | WB | 300000 | 60000 | 70000 | 110000 | 60000 | 300000 | Plan
Actual
| Introdution of short term (professional) courses (design special Agro Bussiness start-up courses for loan takers) | WB | 15000 | 2000 | 5000 | 5500 | 2500 | 15000 | Plan
Actual
| Research grant pools to support faculty and student's international applied research on post-harvest losses | WB | 16000 | 3000 | 4000 | 6000 | 3000 | 16000 | Plan
Actual
| Workshop at AOCAY partner. | WB | 15000 | 3000 | 4000 | 5500 | 2500 | 15000 | Plan
Actual
| Development joint curricula among partnership institution and CEFTER departments | WB | 15000 | 2000 | 5000 | 5500 | 2500 | 15000 | Plan
Actual
| Identification of joint training needs for academic and professional staff in post-harvest science and management | WB | 12000 | 2000 | 3000 | 4500 | 2500 | 12000 | Plan
Actual
| Stakeholders meeting to review progress at ACE | WB | 12000 | 2000 | 3000 | 5000 | 2000 | 12000 | Plan
Actual
| Domestication of curricula in the departments at BSU (Independent review of draft curricula) | WB | 6000 | 1000 | 1500 | 2000 | 1500 | 6000 | Plan
Actual
| Faculty and students training (Staff on PG fellowship) | WB | 20000 | 4000 | 5000 | 7500 | 3500 | 20000 | Plan
Actual
| Mount short courses,workshops and conferences on topics in post-harvest sciences and management (Food Safety and Hygiene) | WB | 15000 | 3500 | 4000 | 4500 | 3000 | 15000 | Plan
Actual
| Institute lecture series: NSPRI organised on Impact of Climate change on PHL | WB | 10000 | 2500 | 2500 | 3000 | 2000 | 10000 | Plan
Actual
| Produce and circulate monographs targeted at awareness creation and extension to rural farmers | WB | 6000 | 1000 | 2000 | 2500 | 500 | 6000 | Plan
Actual
| Support Research fellowships( Sponsor staff of partner institutions on PG programs) | WB | 15000 | 3500 | 3500 | 6000 | 2000 | 15000 | Plan
Actual
| Plan for achieving collaborations with International partners Joint research and Accredition activities (partnership Funding/activities with LJMU) | WB | 35000 | 6000 | 6000 | 15000 | 8000 | 35000 | Plan
Actual
| Start long faculty exchanges between CEFTER, and Universities in Africa | WB | 24000 | 5000 | 6000 | 10000 | 3000 | 24000 | Plan
Actual
| Start of joint research projects between CEFTER,universties and research insttutes elsewhere in Africa | WB | 15000 | 3000 | 3500 | 6000 | 2500 | 15000 | Plan
Actual
Actual
| Produce operational manuals for students | WB | 6000 |  |  | 3000 | 3000 | 6000 | Plan
Actual
| Monitoring and evaluation (Travels, stationaries) | WB | 18000 | 4000 | 4500 | 7000 | 2500 | 18000 | Plan
Actual
| Fund raising activities (Meetings, travels, media) | WB | 10500 | 3000 | 2500 | 4500 | 1500 | 10500 | Plan
Actual
| NgREN Communication Services | WB | 300000 | 60000 | 50000 | 130000 | 60000 | 300000 | Plan
Actual
| Casual staff on Utility services (Cleaners, security) | WB | 40000 | 8000 | 10000 | 14000 | 8000 | 40000 | Plan
Actual
| Provide Automated accounting System | WB | 20000 | 4500 | 6000 | 6500 | 3000 | 20000 | Plan
Actual
|  | TOTAL | 1579000 | 268000 | 310750 | 480500 | 240250 | 1579000
NOTE:
1. operating manuals for students are produced every year.

## CONSULTANCY SERVICES
REVISED SIMPLIFIED PROCUREMENT PLAN FOR ACE PROJECT 2017
1. | General THE EXCHANGED RATE USED IS ₦200 PER US DOLLAR
| Country/Organisation: |  | BENUE STATE UNIVERSITY NIGERIA
| Project/Programme: |  | Center of Excellence in the control of post harvest losses(center for food technology and research)
Loan No:
| Implementing Agency, Address: |  | BENUE STATE UNIVERSITY,MAKURDI,NIGERIA
World Bank's Approval Date of Procurement Plan:
Date of General Procurement Notice:
| Period Covered by these Procurement Plans: |  | January, 2017 – December, 2017
CONSULTANCY SERVICES
2. | Prior Review Threshold:
Consultants (see Note 3)
|  |  |  | Threshold | Prior review
| Procurement Method |  |  | for use of Method | Threshold | Nature of Goods
|  |  |  | (US$) | (US$)
| 1. Quality and Cost Based Selection (QCBS) |  |  | N/A | N/A
| 2. Consultants Qualification Selection (CQS) |  |  | N/A | N/A
| 3. Least Cost Selection (LCS) |  |  | N/A | N/A
| 4. Fixed Budget Selection (FBS) |  |  | N/A | N/A
| 5. Selection of Individual Consultants (SIC) |  |  | N/A | N/A
| 6. Single Source Selection (SSS) |  |  | N/A | N/A
3. |  | PACKAGE NUMBER | SELECTION METHOD | CONTRACT TYPE | ESTIMATED COST | PRIOR/POST REVIEW | PREPARATION & REQUEST FOR PROPOSAL |  | REQUEST FOR EOI (WHERE REQUIRED) |  | SHORTLIST |  | CONSULT PROPOSAL |  | PROPOSAL EVALUATION & NEGOTIATION (TECHNICAL (T), FINANCIAL (F), NEGOTIATION (N)) |  |  |  |  | DRAFT CONTRACT |  | CONTRACT FINALIZATION |  |  |  | CONTRACT IMPLEMENTATION
[7 empty] | PREPARATION & SUBMISSION BY EX. AGENCY | NO OBJECTION | ONLINE UNDB, CLIENT CONNECTION, GATEWAY & NATIONAL PRESS | LEADTIME BEFORE SHORTLIST | SUBMISSION DATE | NO OBJECTION DATE | INVITATION DATE | SUBMISSION/OPENING DATE | SUBMISSION OF EVALUATION REPORT (T) | NO OBJECTION FOR EVALUATION REPORT (T) | OPENING OF FINANCIAL PROPOSAL (F) | PREPARATION OF EVALUATION REPORT (T) & (F) | NEGOTIATION (N) | SUBMISSION DATE | NO-OBJECTION DATE | CONTRACT AMOUNT (US$) | CONTRACT AWARD | DATE OF CONTRACT ADVERT | CONTRACT SIGNATURE | MOBILIZATION ADVANCE PAYMENT | DRAFT REPORT | FINAL REPORT | FINAL COST
[7 empty] | 3-6 WKS | 1-2 WKS | 1-1.5 WKS | 2 WKS |  | 1-2 WKS | 4 WKS TO | 12 WKS | 2-3 WKS | 0.5-2 WKS | 2 WKS | 1-2 WKS | 2 WKS | 1-2 WKS | 1-2 WKS |  | 1 WK |  | 1-3 WKS
|  | Actual |  | AS APPLICABLE
| upgrading established effective quality assurance and quality improvement policy | Plan | I/C |  | 5000 | Post Review | NA | NA | NA | NA | NA | NA | 2nd-May-17 | 18th-May-17 | 10th-jun-17 | 4th-july-17 | NA | 10th-Aug-17 | 2017-08-24 | N/A | N/A | 5000 | 31st-Aug-17 | N/A | 14th-Sep-17 |  | 5th-Oct-17 | 15th-Oct-17 | Actual cost
|  | Actual |  | AS APPLICABLE
| Provide a strong data management policy for CEFTER (Cosultancy charge) and implementation | Plan | I/C |  | 4500 | Post Review | NA | NA | NA | NA | NA | NA | 23rd-May-17 | 4th-Jun-17 | 24th-jun-17 | 22nd-july-17 | NA | 25th-Aug-17 | 6th-Sep-17 | N/A | N/A | 4500 | 13th-Sep-17 | N/A | 7th-Oct-17 |  | 9th-Nov-17 | 18th-nov-17 | Actual cost
|  | Actual |  | AS APPLICABLE
| consultancy services for the construction of PG faculty for cefter complex | Plan | LCS |  | 45037.5 | Post Review | NA | NA | NA | NA | NA | NA | 17th-Jun-17 | 1st-Jul-17 | 17th-Aug-17 | 16th-sept-17 | NA | 29th-Sep-17 | 6th-Oct-17 | NA | NA | 45037.5 | 17th-Oct-17 | NA | 24th-Oct-17 |  | 22nd-Nov-17 | 1st-Dec-17 | Actual cost
|  | Actual |  | AS APPLICABLE
| Environmental And Social Management Plan | Plan | CQS |  | 30000 | Post Review | NA | NA | NA | NA | NA | NA | 24-jan-2017 | 2nd-Feb-17 | 14-Feb-2017 | 1917-02-20 | NA | 15th-Mar-17 | NA | NA | NA | 30000 | 30th-Mar-17 | NA | 10th-Apr-17 |  | 1st-May-17 | 19th-May-17 | Actual cost
AS APPLICABLE
Actual
| Total Cost |  |  | AS APPLICABLE | 84537.5
Note
Please refer to the Bank's comments for enable make the required amendments.
|  |  | Please note that the yellow cells do not require dates, as the project would not be required to send to the WB for Clearance. | [6 empty] | Project should replace the dates with Not Applicable " NA".
1
2

## SUMMARY
SUMMARY
THE EXCHANGED RATE USED IS ₦200 PER US DOLLAR
GOODS
| LOT 1 : RESEARCH/LABORATORY EQUIPMENT | I50,571,43
| LOT 2 : LABORATORY EQUIPMENT | 200287.71
| LOT 3 : STATIONARY/ STAFF COMPUTERS | 40000
| LOT 4 :FURNISHING OF CLASSROOMS | 26507.14
TOTAL |  |  | 417366.28
MINOR WORKS |  |  | 375300
| CONSULTANCY SERVICES |  | 262538
OPERATING COST |  |  | 1429000
GRAND TOTAL |  |  | 2484204.28

## Disbursement Plan
NATIONAL UNIVERSITIES COMMISSION
AFRICA CENTRES OF EXCELLENCE PROJECT (ACE)
CENTRE FOR FOOD TECHNOLOGY AND RESEARCH
CREDIT NO: IDA 54150
DISBURSEMENT PLAN (JANURY - DECEMBER, 2017)
S/N | ACTIVITIES | OBJECTIVE | AMOUNT | MONTHS
|  |  | $ | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | TOTAL
MINOR WORKS
1 | Rehabilitating Existing Facilities: Laboratories and refurblishing of additional Lecture rooms | To refurbish old relevant laboratories to standard | AMOUNT $: 55150; MONTHS FEB: 5515; MONTHS APR: 11030; MONTHS AUG: 38605; MONTHS TOTAL: 55150
2 | Construction of CEFTER PG centre | To Build a new complex containing lecture rooms and food Science Labs | AMOUNT $: 800250; MONTHS FEB: 160050; MONTHS APR: 400125; MONTHS TOTAL: 560175
3 | Establishing of language support unit | To set up a language lab to support students from Francophone countries | AMOUNT $: 19900; MONTHS FEB: 5970; MONTHS APR: 11940; MONTHS SEP: 1990; MONTHS TOTAL: 19900
GOODS
1 | Purchase of Research Equipment | funding to cover cost of small scale research equipment | AMOUNT $: 150571.43; MONTHS FEB: 15057.143; MONTHS MAY: 30114.286; MONTHS JUN: 90342.858; MONTHS OCT: 15057.143; MONTHS TOTAL: 150571.43
2 | Purchase of stationary and staff computers | Funding to cost of stationaries and potable laptops | AMOUNT $: 40000; MONTHS MAR: 8000; MONTHS MAY: 28000; MONTHS DEC: 4000; MONTHS TOTAL: 40000
3 | Use of ICT in delivering Research Excellence :provision of CEFTER PG interactive classroom | Cost of maintenance and upgrade with software subscription | AMOUNT $: 26507.14; MONTHS APR: 5301.428; MONTHS JUN: 13253.57; MONTHS JUL: 5301.428; MONTHS OCT: 2650.714; MONTHS TOTAL: 26507.14
TRAINING
CONSULTANCIES
1 | Upgrading established effective quality assurance and quality improvement policy | Funding to cover cost of developing and producing quality assuarance policy | AMOUNT $: 5000; MONTHS OCT: 5000; MONTHS TOTAL: 5000
2 | Provide a strong data management policy for CEFTER (Cosultancy charge) and implementationy | Funding to cover cost of developing and producing data management policy | AMOUNT $: 4500; MONTHS NOV: 4500; MONTHS TOTAL: 4500
3 | consultancy services for the construction of PG faculty for cefter complex | Funding to cover cost design and consultancy for building | AMOUNT $: 45037.5; MONTHS NOV: 45037.5; MONTHS TOTAL: 45037.5
4 | Environmental And Social Management Plan | Funding to cover cost of ESMP | AMOUNT $: 30000; MONTHS MAY: 30000; MONTHS TOTAL: 30000
OPERATING COST
1 | OPERATING COST | Funding to cover day to day operations | AMOUNT $: 1579000; MONTHS MAR: 394750; MONTHS JUN: 394750; MONTHS SEP: 394750; MONTHS DEC: 394750; MONTHS TOTAL: 1579000
2
| TOTAL |  | 2755916.07 | 0 | 186592.143 | 402750 | 428396.428 | 88114.286 | 498346.428 | 5301.428 | 38605 | 396740 | 22707.857 | 49537.5 | 398750 | 2515841.07

## Contract Data
AFRICAN CENTRE OF EXCELLENCE
CENTRE FOR FOOD TECHNOLOGY AND RESEARCH
BENUE STATE UNIVERSITY
MAKURDI NIGERIA
NIGERIA PROCUREMENT HUB
2017 Prior and Post Review Contracts
ACE, CEFTER, BSU | Works | [9 empty] | Goods | [9 empty] | Consultancy
| ICB |  | NCB |  | Others |  | Total Prior Review Contracts |  | Total Post Review Contracts |  | ICB |  | NCB |  | Others |  | Total Prior Review Contracts |  | Total Post Review Contracts |  | Total Prior Review Contracts |  | Total Post Review Contracts
| # of Contracts | Value ($'000) | # of Contracts | Value ($'000) | # of Contracts | Value ($'000) | # of Contracts | Value ($'000) | # of Contracts | Value ($'000) | # of Contracts | Value ($'000) | # of Contracts | Value ($'000) | # of Contracts | Value ($'000) | # of Contracts | Value ($'000) | # of Contracts | Value ($'000) | # of Contracts | Value ($'000) | # of Contracts | Value ($'000)
|  |  | 3 | 875300 |  |  |  |  | 3 | 875300 |  |  | 1 | 150571.43 | 2 | 66507.14 |  |  | 3 | 217078.57 |  |  | 4 | 84537.5