## Sheet1
Name of Center: Center for Food Technology and Research (CEFTER)
Institution: Benue State University |  |  |  | On Schedule
Country: Nigeria
Center Leader: Dr. Barnabas Achakpa Ikyo |  |  |  | Behind Schedule
Annual Workplan (January-December, 2021)
Work Plan Activities | Description | Partner Contribution (if relevant) | 2021 Y2Q1 |  |  | 2021 Y2Q2 |  |  | 2021 Y2Q3 |  |  | 2021 Y2Q4 |  |  | Milestone/Output | If NEW, Provide Justification | Estimated Budget($) | Estimated Revenue ($) | Contribution from Partner ($) | Person Responsible
|  |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Action 1: DLI 1 Institutional Readine
Sub-Action 1a: Review of existing curricula for relevant PhD programs
Activity 1: Conduct needs assesment | Consider Programs that need to be reviewed | [13 empty] | Students admitted into PhD programs that have been reviewed |  | 2500 |  |  | Departments, Faculty, Postgraduate School
Activity 2: Draft needs assessment for consideration by Technical Committee | List of programs presented for consideration | [15 empty] | 2500
Activity 3: Organise Stakeholders' workshop to review curricula | Invite representatives from the Department involved, Faculty and Postgraduate school for the review | Engage a team of experts in curriculum review | [14 empty] | 20000
Sub-Action 1b: Review of existing curricula for relevant MSc programs
Activity 1: Conduct needs assesment | Consider Programs that need to be reviewed | [13 empty] | Students admitted into MSc programs that have been reviewed |  | 2500 |  |  | Departments, Faculty, Postgraduate School
Activity 2: Draft needs assessment for consideration by Technical Committee | list of programs presented for consideration | [15 empty] | 2500
Activity 3: Organise Stakeholders' workshop to review curricula | Invite representatives from the Department involved, Faculty and Postgraduate school for the review | Engage a team of experts in curriculum review | [14 empty] | 20000
Sub-Action 1c: Establishment of new Partnership
Activity 1: Conduct needs assesment | Get a suggestion of prospective partners | [13 empty] | Partners involved in teaching, training and research activities |  | 1000 |  |  | Project Technical Committee
Activity 2: Draft needs assessment report for consideration by Technical Committee | Technical committee to consider suggestions | [15 empty] | 1000
Activity 3: Write to new Partners | Write to New partners to seek their consent | Partners are communicated | [14 empty] | 1000
Activity 4: Develop an MoU | Develop an MoU that is acceptable to both parties | Consider MoU | [14 empty] | 1000
Activity 5: Sign MoU with new Partners | Sign MoU | Sign MoU | [14 empty] | 6000
Action 2: DLI 2: Development Impact
Sub-Action 2a: Second West and Central Africa Post Harvest Congress
Activity 1: Hold Planning Meetings | Hold a meeting to assign responsibilities and set up committees | Participate in meetings, share responsibilities | [12 empty] | Congress successfully planned, venue located and paid for |  | 20000 |  |  | Centre Management
Activity 2: Stakehoder Drive | Consider possible stakeholders and inform them | Suggest stakeholders | [14 empty] | 20000
Activity 3: Venue | Get a venue for the congress and pay for it | [15 empty] | 15000
Activity 4: Feeding at the Congress | [16 empty] | 10000
Activity 5: Conference bags and other materials | [16 empty] | 5000
Activity 6: Travels(Local and International) | [16 empty] | 40000
Sub-Action 2b: Participation at Regional Conferences and Seminar by Staff and Students
Activity 1: Conduct needs assesment | Consider requests for regional conference attendance by Staff and students | [13 empty] | Mainstreaming of improved learning and teaching methods in the institutions |  | 2500 |  |  | Centre Management
Activity 2: Travel and accommodation cost for staff and students at regional Conferences | For those approved, provide for the expenses involved | [15 empty] | 15000
Activity 3: Prepare report/proceedings and circulate | Reports submitted by staff and students on return from regional conference will be put together and circulated | [15 empty] | 2500
Sub-Action 2c: National Conference and Seminar by Staff and Students
Activity 1: Conduct needs assesment | Hold a meeting to consider modalities towards a national conference and seminar for Staff and Students | [13 empty] | Mainstreaming of improved learning and teaching methods in the institutions |  | 1250 |  |  | Centre Management
Activity 2: Organise national stakeholder workshop | Organise workshop for staff and students to come together and discuss problems of teaching, learning and research | [15 empty] | 7500 | 1500
Activity 3: Prepare report/proceedings and circulate | Prepare report/proceeding of the workshop and circulate | [15 empty] | 1250
Sub-Action 2d: Produce and Circulate flyers, Posters and Monographs
Activity 1: Conduct needs assesment | Consider contents and type of the documents to be published | [13 empty] | Flyers, Posters and Monographs in circulation |  | 2000 |  |  | Centre Management
Activity 2: Prepare report and submit to Technical committee for consideration | Presents considerations to the Technical committee | [15 empty] | 1000
Activity 3: Set up an editorial unit and print approved quantity of fliers | Set up editorial unit to produce appoved items | [15 empty] | 12000 | 2400
Sub-Action 2e: National/Regional Post-harvest Clinic/activities
Activity 1: Conduct needs assesment | Consider improved techniques for food preservation and processing | Suggest new techniques | [12 empty] | Community members adopt improved techniques for food preservation and processing |  | 4000 |  |  | Centre Management
Activity 2: Draft report for consideration by Technical Committee | Present considerations to technical committee for | [15 empty] | 1000
Activity 3: Identify Communities for participatory conduct of Post-Harvest Clinic | Consider the target prticipants from Regional and National communities for the Clinic | Make suggestions | [14 empty] | 5000
Activity 4: Design curriculum and train resource persons from the communities | Training of persons from different communities on post-harvest activities | Participate in trainings | [14 empty] | 10000
Action 3: DLI 3: Quantity of Students
Sub-Action 3a: Developement and Training of Farmers/Food Handlers in Safe Hygiene, Transportation of Produce to Markets
Activity 1: Conduct needs assesment | Hold a meeting to set out modalities for the training | Participate in meetings | [12 empty] | Use of new modules by farmers/food handlers to improve their income |  | 500 |  |  | Centre Management
Activity 2: Prepare report and submit to Technical committee for consideration | Draft a report for the training and submit to Technical Committee | [15 empty] | 500
Activity 3: Organise Stakeholders' workshop for industries and local fabricators | Organise Stakeholders' workshop | Participate in workshop | [14 empty] | 3000
Activity 4: Identify suitable modules for safe transportation of fruits and vegetables, grains, roots and tubers | Identify modules that are suitable for the training | Suggest modules | [14 empty] | 500
Activity 5: Identify suitable communities to test run the modules | List out communities in which the modules will be tested | Suggest communities | [14 empty] | 500
Activity 6: Train community members in the use of developed modules | Community members will be trained in the use of the modules | Participate in trainings | [14 empty] | 5000 | 1000
Sub-Action 3b: Training of Faculty in Innovative University Teaching
Activity 1: Conduct needs assesment | Hold meeting to outline training modalities | Join meetings | [12 empty] | Increase in number of faculty using innovative teaching methods, students benefiting from new innovative teaching methods |  | 2000 |  |  | Centre Management
Activity 2: Draft needs assessment report for consideration by Technical Committee | Submit draft to Technical committee for consideration | [15 empty] | 1000
Activity 3: Organise Trainer of Trainers Workshop involving new partners in innovative teaching and supervision | Train the Trainers on innovative University teaching | Conduct trainings | [14 empty] | 6000
Activity 4: Mobilise partners for cascade training and mainstreaming innovative teaching methods in institutions and schools | The Trainers disseminate knowledge acquired in institutions and schools | [15 empty] | 11000
Sub-Action 3c: Implementation of Short Term Courses(Including Online)
Activity 1: Conduct needs assesment to identify three to four countries in West and Central Africa for training | Identify Countries in West and Central Africa for the training | Make suggestions | [12 empty] | Graduates from short term courses employed or establishing businesses |  | 10000 |  |  | Centre Management
Activity 2: Develop a suitable curriculum for training. Train resource persons in country and identify trainees | Identify trainees and train resource persons using a suitable curriculum | Suggest trainees | [14 empty] | 10000
Activity 3: Develop program and implement | Implement the short courses | Implement short courses | [14 empty] | 20000 | 4000
Sub-Action 3d: Training of Technologist and Laboratory Automation
Activity 1: Conduct needs assesment to identify the areas of need | Identify the areas that require training of technologists | [13 empty] | Trained laboratory technologists deployed to the departments |  | 5000 |  |  | Centre Management
Activity 2: Conduct survey to identify national and international institutions with best training facilities | Consider available institutions with the best training facilities nationally and internationally | [15 empty] | 2000
Activity 3: Identify and send suitable candidates for training | Send candidates for training | Conduct trainings | [14 empty] | 33000
Sub-Action 3e: Student Recruitment
Activity 1: Advertise Senate approved programs on CEFTER website | Place application advert for on CEFTER website | [13 empty] | Students register and resume lectures |  | 2500 |  |  | Centre Management
Activity 2: Advertise Senate approved programs on local and regional print media | Advertise programs on local, regional and print media | [15 empty] | 12500
Activity 3: Technical committee meets to consider shortlisted candidates for admission | Shortlisting of qualified candidates for admission | [15 empty] | 2500
Activity 4: Postgraduate Board meets and approves admission list | Approval of admission list | [15 empty] | 2500
Sub-Action 3f: Student Support/Scholarships
Activity 1: Conduct needs assesment | Call for applications for Student Support/Scholarship | [13 empty] | Students receive support/scholarship letters |  | 5000 |  |  | Centre Management
Activity 2: Students Complete application forms seeking for support/scholarship | Interested applicants apply for Support/Scholarship
Activity 3: CEFTER Scholarship and Grants Allocation Committee meets to Shortlist qualified students | Qualified students shortlisted for the award | [15 empty] | 5000
Activity 4: Shortlisted students forwarded to the Vice Chancellor for Approval | Vice Chancellor considers the list for approval
Activity 5: Funding for scholarship awarded to students annually. Covers tuition, accommodation and living expensis | Award of Support/scholarship | [15 empty] | 120000
Sub-Action 3g: Setup of Phd Offices
Activity 1: Design of PhD offices | Design offices for PhD students | [13 empty] | Furnished offices available for PhD students |  | 5000 |  |  | Centre Management
Activity 2: Furnishing of the offices | Furnish offices | [15 empty] | 45000
Sub-Action 3h: Training of Students/Staff on use of ICT for learning
Activity 1: Conduct needs assessment | Conduct needs assessment | [13 empty] | Students and Staff using advanced software for their learning/teaching and research |  | 500 |  |  | Centre Management
Activity 2: Identify the software suitable for enhanced students learning | Identify suitable software for enhanced student learning | Suggest suitable software | [14 empty] | 500
Activity 3: Identify and engage a suitable resource person | Engage suitable resource persons | Suggest resource persons | [14 empty] | 1000
Activity 4: Organise training | Organise training sessions | [15 empty] | 13000
Action 4: DLI 4: Quality of Education/Research
Sub-Action 4a: CEFTER Thematic Annual Research Grant
Activity 1: Hold planning meetings | Hold meetings to plan and send out call for grant applications | [13 empty] | Annual Grant successfully awarded |  | 10000 |  |  | Centre Management
Activity 2: Receive and review applications | Review received applications | Review applications | [14 empty] | 5000
Activity 3: Award grants | Award grants to application that meet the set criteria | [15 empty] | 35000
Sub-Action 4b: Funding Peer Reviewed publications from CEFTER Staff and Students
Activity 1: Students and faculty publications submitted to CEFTER publications committee | Publications by students and faculty submitted to committee for consideration | [13 empty] | Number of publications verified and accepted by Association of African Universities (AAU) monitoring committee |  |  |  |  | Centre Management
Activity 2: The committee reviews and shortlists good quality publications | Good quality publications are selected | [15 empty] | 1000
Activity 3: Shortlisted publications sent to experts for peer review | Selected publications sent for review | [15 empty] | 1000
Activity 4: Payment of publication charges | Payment of publication charges | [15 empty] | 4000
Activity 5: Subscription to Journals | Subscription to Journals | [15 empty] | 4000
Sub-Action 4c: Construction of CEFTER Food Technology Innovation Complex (CEFTIC)
Activity 1: Conduct needs assesment | Determine the specifications of the complex and make a report | [13 empty] | CEFTER Food Technology and Innovation Complex in use |  | 2000 |  |  | Centre Management
Activity 2: Draft report for consideration | Submit report for consideration | [15 empty] | 1500
Activity 3: Submit Proposal to procurement committee | Proposal for construction submitted to procurement committee | [15 empty] | 1500
Activity 4: Advertise for tenders | Advertise for tenders | [15 empty] | 10000 | 2000
Activity 5: Award contract | Contract awarded for construction and installation | [15 empty] | 685000
Sub-Action 4d: Procurement of Small Equipment and Consumables
Activity 1: Conduct needs assesment with departments and partners | Get a comprehensive list of equipments and consumables needed | [13 empty] | Students and Staff enjoying facilities procured for research and teaching |  | 2500 |  |  | Centre Management
Activity 2: Draft report for consideration | Consider report | [15 empty] | 1500
Activity 3: Submit Proposal to procurement committee | Submit proposal to procurement committee | [15 empty] | 1000
Activity 4: Advertise for tenders | Advertise for tenders | [15 empty] | 5000 | 1600
Activity 5: Contract awarded for purchase and installation (GCMS for Chemistry lab, FITR Spectrometer, Software and informatics) | Award contract | [15 empty] | 60000
Sub-Action 4e: Installation of 50Kva Solar Power to the new CEFTER Complex
Activity 1: Conduct needs assesment | Hold meeting to consider and prepare a report for the installation | [13 empty] | Students and Staff enjoying supplementary solar power |  | 12500 |  |  | Centre Management
Activity 2: Draft report for consideration | Consider report for installation, write proposal | [15 empty] | 12500
Activity 3: Submit Proposal to procurement committee | Procurement committee consider proposal
Activity 4: Advertise for tenders | Advertise for tenders | [15 empty] | 25000 | 5000
Activity 5: Contract awarded for purchase and installation of Solar panels, Batteries, Inverters and smart grid system | Award contract | [15 empty] | 85000
Sub-Action 4f: Student-Faculty Grant (CPSS)
Activity 1: Students and faculty complete and submit application form | Call for and receive applications for grants from Sudents and Faculty | Submit applications | [12 empty] | Student and Faculty conducting research on approved projects |  |  |  |  | Centre Management
Activity 2: The Scholarship and Grants Committee meets and shortlists candidates for interview | Cosider applications and shortlist candidates for interview | Participate in consideration of applications and shortlisting | [14 empty] | 2500
Activity 3: Shortlisted candidates defend their proposals before the committee | Proposal defence by shortlisted candidates | Proposal defence | [14 empty] | 2500
Activity 4: Disbursement to successful grant applicants | Successful candidates receive disbursement | [15 empty] | 25000
Sub-Action 4g: Establishment of Regional Research Groups
Activity 1: Conduct needs assesment for establishment of regional working groups | Hold meetings to consider the available networking options and advantages | Participate in meetings | [12 empty] | Joint publications in high quality Journals |  | 4000 |  |  | Centre Management, Regional Partners, Heads of Departments
Activity 2: Organise a regional faculty stakeholders workshop to formation of regional working groups and how to network | Organise workshops to form regional groups and consider networking options | Participate in workshops | [14 empty] | 14000
Activity 3: Draft reports and share | Draft and share reports | [15 empty] | 2000
Action 5: DLI 5: Relevance of Education/Research
Sub-Action 5a: Partnership Activities
Activity 1: Training of Staff at MSc, PhD levels: Study fellowship | Staff considered for study fellowship | Train Staff at MSc and PhD levels | [12 empty] | Completion of agreed activities for each quater |  | 80000 |  |  | Project Technical Committee
Activity 2: Student Internships (This includes accomodation, monthly stipend, transport, supervision and consumables) | Students engaged on internships | Organise internships | [14 empty] | 80000
Activity 3: Joint Projects | Joint activities with partners | Jiont activities | [14 empty] | 50000
Activity 4: Short courses training: Local and international travels | Local and international participation in short courses | Participation in short courses | [14 empty] | 70000 | 14000
Sub-Action 5b: Faculty and Students Food Post-harvest Week
Activity 1: Conduct needs assesment | Formulate student groups | [13 empty] | Students and Entrepreneurs establish businesses using processed food products. Successful patentingof some food products |  | 1000 |  |  | Centre Management
Activity 2: Identify crops and assign to students groups | Assign specific crops to student groups | [15 empty] | 1000
Activity 3: Assign faculty to student groups as mentor | Assign faculty to each student group to serve as mentor | [15 empty] | 1000
Activity 4: Student identify food products and prepare budgets | Students prepare and submit budgets | [15 empty] | 8000
Activity 5: Funding | Funds released for raw materials and accessories for the food week | [15 empty] | 14000
Sub-Action 5c: CEFTER Enterprise Development
Activity 1: Hold planning meetings | Call for applications on enterprise development | [13 empty] | One startup per year |  | 10000 |  |  | Centre Management
Activity 2: Receive and review applications | Review submitted applications | Review applications | [14 empty] | 15000
Activity 3: Setup small and medium scale Funding for three year start-ups per year. 3 winning groups in the enterprise competition will use the fund to set up an agro based small scale enterprise | Consider successful applications for small and medium scale funding for start-ups | Consider applications | [14 empty] | 75000
Sub-Action 5d: Provision of Extension and Community Awarness on Post-Harvest Losses
Activity 1: conduct needs assesment | Draft out report on community awareness process | Participate in meetings | [12 empty] | Members of the Community adopt improved processing and preservation techniques |  | 1000 |  |  | Centre Management
Activity 2: Prepare report and submit to Technical Committee for consideration | Submit report for consideration | Consider report | [14 empty] | 1000
Activity 3: Prepare a report on level of post-harvest losses accross crop value chain in West and central Africa | Project the level of post harvest losses across West and Central Africa | [15 empty] | 3000
Activity 4: Organise yearly community awareness campaigns in selected countries in West and Central Africa | Organise awarenesses campaigns | Engage in campaigns | [14 empty] | 10000
Sub-Action 5e: Student Intership
Activity 1: Conduct needs assesment | Consider the different areas for students internships | Present internship areas | [12 empty] | Students deployed to institutions for internship |  | 2000 |  |  | Centre Management
Activity 2: Identify Industrial and sectoral Partners for students' internship | Identify the Industries and Sectoral partners that can meet the internship needs | Identify industries and partners
Activity 3: Develop internship manuals | Develop manuals for internship | Develop manuals | [14 empty] | 1000
Activity 4: Develop Schedule for Student distribution | Prepare a student distribution schedule | [15 empty] | 12000
Sub-Action 5f: Setup and maintenance of graduate Tracking System
Activity 1: Hold planning meetings | Plan on the modalities for setting up a graduate tracking system | [13 empty] | Tracking of CEFTER graduates from 2016-2018 |  | 1000 |  |  | Centre Management
Activity 2: Development and hosting of graduate tracking system online | Develop an online graduate tracking system | [15 empty] | 5000
Activity 3: Salary for 2 staff in the graduate tracking unit | Payment of staff involved | [15 empty] | 9000
Sub-Action 5g: Fund Raising Activities
Activity 1: Conduct needs assesment | Conduct needs assessment | [13 empty] | The project achieves up to 40% of IGR |  |  |  |  | Centre Management
Activity 2: Prepare report and submit to Technical Committee | Submit report to technical committee for consideration | Consider Report | [14 empty] | 2000
Activity 3: Organise Stakeholders workshop to brainstorm and identify fund raising activities | Organise workshop for stakeholders to consider and select fundraising activities | Organise workshops, suggest activities | [14 empty] | 10000 | 2000
Activity 4: Implement fund raising activities | Implement the activities | Facilitate activities | [14 empty] | 18000 | 3600
Sub-Action 5h: Grant Application:
Activity 1: Hold planning meetings | Hold meetings and consider available grants | Suggest grant winning ideas | [12 empty] | 3 grants applications submitted each year |  | 2000 |  |  | Centre Management
Activity 2: Write and apply for grants | Apply for grants | Facilitate applications | [14 empty] | 8000
Action 6: DLI 6: Timeliness/Quality of Financial Management
Sub-Action 6a: Procurement and Installation of ICT Facilities at the new Postgraduate Centre
Activity 1: Conduct needs assesment | Prepare report on ICT needs at the new Postgraduate centre | [13 empty] | Students and Faculty using ICT facilities for teaching and research |  | 2500 |  |  | Centre Management
Activity 2: Draft report for assessment by Technical Committee | Technical committee to consider report | [15 empty] | 1500
Activity 3: Submit report to Procurement Committee | Report submitted to procurement committee for cinsideration | [15 empty] | 1000
Activity 4: Advertise for tenders | Advertise for tenders | [15 empty] | 5000 | 1000
Activity 5: Contract awarded for purchase and installation(Server and facilities, interactive board and projectors, internet service subscription) | Award of contract | [15 empty] | 60000
Activity 6: Maintenance of installation | Maintenance of facilities installed
Sub-Action 6b: Regional Project Review Workshops
Activity 1: Identify and notify participants | Identify and notify regional workshop participants | [13 empty] | Management identifying areas of weakness for improvement |  | 1500 |  |  | Centre Management
Activity 2: Prepare update report on project | Prepare update report on project | [15 empty] | 1000
Activity 3: Submit to CEFTER technical Committee for inputs | Submit report to technical committee for consideration | [15 empty] | 1000
Activity 4: Travels and accomodation cost | Settle workshop expenses | [15 empty] | 26500
Sub-Action 6c: Internal Monitoring and Evaluation Activities
Activity 1: Conduct needs assesment | Consider all M&E activities and report | [13 empty] | Internal monitoring teams ensure timely response to all AAU monitoring requirements |  | 500 |  |  | Centre Management
Activity 2: Prepare and present report to Technical Committee for consideration | Technical committee to consider report | [15 empty] | 500
Activity 3: Set up an M&E committee under the chairmanship of the M&E officer | Set up M&E committee | [15 empty] | 1000
Activity 4: Conduct quaterly review of all CEFTER activities to ensure they meet desired quality and deadlines | Review CEFTER activities quaterly | [15 empty] | 3000
Action 7: DLI : Institutional Impact
Sub-Action 7a: Development and Implementation of FLIP Classroom
Activity 1: Conduct needs assesment | Prepare report on Implementation of FLIP classroom | [13 empty] | Students and Staff making use of FLIP classrooms |  | 1000 |  |  | Centre Management
Activity 2: Draft report for consideration | Consider report and prepare proposal
Activity 3: Submit proposal to Procurement Committee | Submit proposal to communication committee for consideration
Activity 4: Advertise for tenders | Advertise for tenders | [15 empty] | 4000 | 1800
Activity 5: Contract awarded for purchase and installation(Furnishing of lecture recording studio and procurement of recording cameras and electronics) | Award of contract | [15 empty] | 35000
Sub-Action 7b: Expansion of Language Support Unit
Activity 1: Conduct needs assesment | Consider the need for an expansion and draft out modalities | [13 empty] | Language Support facilities being used by CEFTER to conduct bilingual meetings |  | 1000 |  |  | Centre Management
Activity 2: Meet with experts from department of Languages and Linguistics | Meet with experts from Languages and Linguistics department | [15 empty] | 1000
Activity 3: Draft Language support unit guidelines | Draft guidelines for the language support unit | [15 empty] | 2000
Activity 4: Procure more Language translation gadgets | Procure aditional Language translation gadget | [15 empty] | 13000
Activity 5: Train personnel in the use of gadgets | Train personnel on the use of gadgets | [15 empty] | 3000
Sub-Action 7c: Purchase of Project utility vehichles(1 Hilux pickup van and 30 seater Bus)
Activity 1: Conduct needs assesment | Consider the need for the purchase of utility vehichles, prepare report | [13 empty] | Utility vehicles in use by Staff and Students |  | 1000 |  |  | Centre Management
Activity 2: Advertise for tenders | Advertise for tenders | [15 empty] | 2000 | 400
Activity 3: Funding for purchase of Hilux truck | Funding for purchase | [15 empty] | 55000
Activity 4: Funding for purchase of 30 seater Coaster bus | Funding for purchase | [15 empty] | 122000
Sub-Action 7d: Institutional Reforms for Regional strategy (institutional accreditation, participation in PASET initiative and promotion of institutional impact)
Activity 1: Conduct needs assesment | Identify and prepare report on different areas of institutional reforms | [13 empty] | Institutional accreditation achieved when due |  | 2000 |  |  | Centre Management
Activity 2: Draft report and present to CEFTER Technical Committee | Present report to Technical Committee for consideration | Consider different areas of reforms, and make contributions where applicable | [14 empty] | 2000
Activity 3: Draft report and present to Vice chancellor to guide him on institutional reforms | Present report to Vice Chancellor on selected areas of reform for implementation | [15 empty] | 26000
Note on V6: Schenineda: If the addition of an activity or component requires further clarification, state it. Expecially since COVID may alter center activities and focus